## Url
Project Details
Project Name: | Poonam Coating ERP
Date: | 26.04.24
Client Name: | Manish Manhotra
Prepared By: | Ronak Patel
Reference Document
Source Document - SRD/BRD: | ERP Version 1
Source Document - SRD/BRD: | ERP_Version2
Figma Link: | https://www.figma.com/design/BoxMekdUPy0HqBjZWkYcBo/ERP-Poonam-Coatings?node-id=1260-13427&t=E1pDqfARwJPYG4ip-0
Website link for testing :
Credential
User Name:
Password: | Na
For User Login
User Name: | ronakriya@poonamcoatings.com
Password: | Ronak@1997 Format: Username with First letter caps + @ + year
Phase I Module Details | Dashboard + Profile Buyers & Suppliers Calendar Management Settings User Management Email Management
Phase II - Module Details | Settings Company Management Department Management Product Management Product Catalogue Inventory

## Scenarios
ERP Of Poonam Coatings
Sr. No. | Test Scenarios | URL
1 | Sign Up Page | Sign Up
2 | Login Page | Login Page
3 | Dashboard | Dashboard
1 | Profile | Profile Management
2 | Buyer And Suppplier Management | Buyers and Suppliers
3 | User Management | User Management
4 | Company Management | Company Management
5 | Product Management | Product Management
6 | Email Management | Email Management
7 | Department Management | Department Management
8 | Stock Management | Stock Management
9 | Product Catalogue | Product Catalogue
10 | Inventory Management | Inventory
11 | Sale | Sales
1 | Bug Report Summary | Bug Summary Report

## Login
DATE OF CREATION | 24.04.24 |  |  |  | TOTAL PASS
MODULE NAME | Login |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS |  |  |  |  | TOTAL TEST CASES | 0
Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
My Profile | [5 empty] | Pass
Pass
Fail
2.6

## Sign Up
DATE OF CREATION | 24.04.24 |  |  |  | TOTAL PASS
MODULE NAME | Sign Up |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS |  |  |  |  | TOTAL TEST CASES | 0
Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
My Profile | [5 empty] | Pass
2.6

## Dashboard
DATE OF CREATION | 29.04.24….08.05.24 |  |  |  |  | TOTAL PASS | 19
MODULE NAME | Dashboard |  |  |  |  | TOTAL FAIL | 12
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 31
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
29.04.24 | Header-Top | Verify Notification functionality |  |  |  |  | Fail
|  | Verify See more button functionality |  |  |  |  | Remaining to check
|  | Verify Profile redirect on profile page |  |  | Redirects on the Profile Page | Same as Expected Result | Pass
|  | Verify search button functionality |  |  | It should not be required here, It may create confusion. There is no any role for search button. | Not searching anything | Pass | https://cuneiform.atlassian.net/browse/ECPC-213 |  |  |  |  | Done | 06.06.24
|  | Verify Header UI |  |  | shape should be same for all | Similar to Figma, the slightly rounded shape of the rectangular box looks fantastic. A rounded curve appears more here. A small curvature appears nice. | Fail | https://cuneiform.atlassian.net/browse/ECPC-214
|  | Verify Humburger Menu items |  |  |  |  | Remaining to check
| Dashboard title | Verify date period title |  |  | Here when we hover on date, color is changed just like clickable. It should be display with one color like red. Hover will create the confusion | It displays the title of date period like below: August 1,2020 - August 31,2020 | Fail | https://cuneiform.atlassian.net/browse/ECPC-215
|  | Verify Action button work |  |  |  |  | Remaining to check
|  | Verify Download button functionality |  |  |  | Not working | Remaining to check
|  | Verify print button functionality |  |  |  | Not working | Remaining to check
| Production/Manufacturing Status | Verify month/Week/Day |  |  | When we hover on, color should be change like Red | Same as Expected Result | Pass
|  | Verify title Production / Manufacturing Status |  |  | It should be “Production Manufacturing Stats.” |  | Fail | https://cuneiform.atlassian.net/browse/ECPC-216 |  |  |  |  | Assign back Not done Here it displays like “Production Manufacturing Status” . It should be “Production Manufacturing Stats” Because we have used title in “Buyers And Suppliers” “Company Stats”. Both title should be same. You can use Status or stats, but in both title. | 06.06.24
|  | Verify title path home/Analytic |  |  | It is missing |  | fail | https://cuneiform.atlassian.net/browse/ECPC-217 |  |  |  |  | Path seems wrong in each option. Changes have been done by designer pls check Figma and so it accordingly. | 06.06.24
| Weekly Stats | Verify Production manufacturing Stats of chart (Top Sales/Best Seller/Most Commented) |  |  |  |  | Remaining to check
|  | Verify Weekly Stats |  |  |  |  | Remaining to check
|  | Verify text Average sale |  |  | It should be "Average Sale" | Average sale | Pass | https://cuneiform.atlassian.net/browse/ECPC-218 |  |  |  |  | Removed by developer
| Revenue Updates | Verify Revenue Updates |  |  |  |  | pass
|  | Verify month Filter dropdown functionality |  |  | Month should be selectable from dropdown list | As per expected result | pass
|  | Verify chart should be changed by selected month |  |  | Chart should be changed | Chart is consistant for all month | Remaining to check
|  | Verify View full Report |  |  |  |  | Remaining to check
|  | Verify Total Earnings /Earning this month/Expenses this month |  |  | text should be in proper case | Not arranged | fail | https://cuneiform.atlassian.net/browse/ECPC-219 |  |  |  |  | Not done | 06.06.24
|  | Verify text UI |  |  | All text should be arranged like below: First Title then value Total Earnings Rs. 63,489.50 Earning This Month Rs. 48,820 Expense This Month Rs. 26,498 | It is not arranged as expected result here In First - value then text means Rs. 63,489.50 Total Earnings Earning This Month Rs. 48,820 Expense This Month Rs. 26,498 | Pass | https://cuneiform.atlassian.net/browse/ECPC-220 |  |  |  |  | Done | 06.06.24
| Revenue Updates | Verify Calander works |  |  | It should display current month | not displyed | pass
| Buyers & Suppliers | Verify dropdown for date |  |  | Select month form the drop down list | same as expected result | pass
|  | Verify title of Name/City/Date/Budget |  |  | It should be Name/City/Date/Budget | As per expected result | pass
|  | Verify budget should be display in Rs. Or ₹ |  |  | It should be ₹. CRM will be used in India only for now. For display purpose, it looks realistic. | Here $ comes in budget | Pass | https://cuneiform.atlassian.net/browse/ECPC-221 |  |  |  |  | Done | 06.06.24
|  | Verify Buyers and Suppliers |  |  |  |  | Pass
| Recent Updates | Verify Recent Updates-Its functionality work |  |  |  |  | Remaining to check
| Footer | Verify link for About Us/Contact Us/Services |  |  | should be redirect on their specific page |  | Pass
|  | Verify text - Copyrights @2024 Poonam Coatings, All Rights Reserved |  |  | Footer design looks not good. | Please refer screenshot of sparepartwale it looks good | fail | https://cuneiform.atlassian.net/browse/ECPC-222 | 1 |  |  |  | Not done
| Logo in header | Verify logo is in left side corner |  |  |  |  | Pass | https://cuneiform.atlassian.net/browse/ECPC-223 |  |  |  |  | Commented by dev - After moving the logo it does not look good so this change is not accessory | 06.06.24

## Buyers and Suppliers
DATE OF CREATION | 01.05.24 - Test cases Bug Assigned - 13.05.24 |  |  |  |  | TOTAL PASS | 76
MODULE NAME | Buyers and Suppliers |  |  |  |  | TOTAL FAIL | 38
REDIRECT ON SCENARIOS | Back |  |  |  |  | TOTAL TEST CASES | 114
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Actual Result | Status | JIRA Ticket ID# | Screenshot | Designer Bugs | Designer Comment | Developer Comment 1 | Developer Comment 2 | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
01.05.24 | Header | Verify Search button |  |  | Search button is not required on header |  | pass | https://cuneiform.atlassian.net/browse/ECPC-137 | [5 empty] | Done 18.06.24
|  | Verify Notifications |  |  |  |  | Remaining to check
|  | Verify Profile should be redirect to profile page |  |  |  |  | pass
|  | Verify logout button functionality |  |  |  |  | pass
| Buyers and Suppliers | Verify text of Categories/City/Tags |  |  |  |  | pass
| Buyer and Suppliers | Verify Add Buyers/Suppliers-UI Design |  |  | All text box sizes should be the same. here Pink text box looks slightly big. Its shape should be a rounded rectangle please refer to Figma. The search icon box also looks different. Please arrange all text boxes in line. | Text boxes are not in line. Text box of Add Buyers/Suppliers shape is different. | pass | https://cuneiform.atlassian.net/browse/ECPC-138 | Check screenshot |  |  |  |  | Done 18.06.24 |  | Done
|  | Verify dropdown of Add Buyers and Suppliers |  |  | It should be add Single company and Multiple company |  | pass
|  | Verify tag functionality-it is for comment only |  |  |  |  | Remaining to check
|  | Verify title of Company/City/Tags/Date/Actions |  |  | Title should be came like Company/City/Tags/Date/Actions | Tags are missing. It should be there. | Pass
|  | Verify Company Name, City, Tags format |  |  | Company Name, City, Tags should be came with proper case | For now tags are not available | pass
| Buyer and Suppliers-Title | One column should be there i.e company type |  |  | one new column should be added in the title of buyers and Suppliers. So, by viewing of table admin/manager can understand added company is a Buyers or Suppliers |  | pass | https://cuneiform.atlassian.net/browse/ECPC-139 | [5 empty] | Done 18.06.24
|  | UI for Buyers and Suppliers |  |  |  |  | Pass
|  | Verify date format |  |  | date should be came with proper format | As per expected result | pass
|  | Verify Action button edit functionality |  |  | After clicking on the edit button, it should be redirected on buyers/supplier edit page | As per expected result | pass
|  | Verify Action button delete functionality |  |  | After clicking on the edit button, it should be redirected on buyers/ suppliers delete pop up | As per expected result | pass
|  | Verify Pegination |  |  | User can able to go at different pages with the use of pegination |  | pass
|  | Verify functionality of the next and Previous arrow button |  |  | Should be able to next and previous page |  | pass
|  | Verify View button |  |  | View button should be there in action. | Not available | pass | https://cuneiform.atlassian.net/browse/ECPC-153 | [5 empty] | Done 18.06.24
| Add Single Buyers/Suppliers | Verify Add Single buyers button functionality |  |  |  |  | pass
| Add a New company Pop UP | Verify title of Add A New Company |  |  | The title should be "Add New Company". Please update the title to "Add New Company" | Here it is "Add A New Company". Title is correct but it does not look good. | pass | https://cuneiform.atlassian.net/browse/ECPC-140 | [5 empty] | Done 18.06.24
|  | UI for Buyers and Suppliers |  |  |  |  | pass
|  | Personal Info-Verify title Name/Phone/Email |  |  | All titles should be correct. Here "Name title comes but it should be "Full Name". please update the "Name" To "Full Name". We have already taken the “Full Name” title in the “Edit Information” module. | The title comes as "Name". | pass | https://cuneiform.atlassian.net/browse/ECPC-141 | [5 empty] | Done 18.06.24
|  | Verify Full name - It should be min 3 characters and maximum 80 characters allowed. |  |  |  |  | pass
|  | Verify First letter of the name should be converted into capital when a user enters information. |  |  |  |  | pass
|  | Verify Digit is not allowed |  |  | digit should not be allowed |  | pass
|  | Verify validation message of "Name" for maximum character |  |  | It should be "Full Name must be less than 80 characters" | Name must be less then 80 characters. Please update it with below : "Name must be less than 80 characters." | pass | https://cuneiform.atlassian.net/browse/ECPC-142 | [5 empty] | Done 18.06.24
|  | Verify validation message of Name for minimum characters |  |  |  |  | pass
|  | Verify validation message of email address |  | test@.com text@com 123@gmail.com | It should be "Invalid email address". Also when user hover on text box of email address then one message should be displayed for its format. Check screenshot | Complete email address Please update with "Invalid email address" | Pass | https://cuneiform.atlassian.net/browse/ECPC-143 | 1.2 |  |  |  |  | Done but suggestion message not comes after hover on Assign back 19.06.24 | Assign back 04.07.24
|  | Verify Space is not allow |  | test hjh@gmailcom | It should not be allowed | As per expected result | pass
|  | Verify contact should be 10 digit. |  | 5454454556 8788678888 0000000000 | It should not be allowed more than 10 digits | As per expected result | pass
|  | Verify characters and special characters are not allowed |  |  |  |  | pass
|  | Verify to entering right/wrong email Id |  |  |  |  | pass
|  | Company Details - Verify company details like Company Name/Company Reference ID/Official Email Address/Company Contact No./GST Number/Company Type /Address Location 1/Address Location 2/Pincode/City/State |  |  |  |  | pass
|  | Verify when user entering the name, First letter of name should be automatically converted in to capital |  |  |  |  | pass
|  | Verify company name has a limit of characters |  |  |  |  | pass
|  | Verify validation message for minimum characters in company name |  | hj | Company name must be at least 3 characters long | As per expected result | pass
|  | Verify validation message for maximum characters in company name |  | gjhggjhgjhgjhgjhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhhh | It should be "Name must be less than 80 characters |  | pass
|  | Verify digit in company name |  | Forever 21 Big 5 sporting goods 21st Century Fox Century Pvt Ltd | Some company name has a digit along with their name . | Here digit is not allowed in company name. Digit should be allowed in company name i.e Forever 21 Big 5 sporting goods 21st Century Fox 3blmedia | pass | https://cuneiform.atlassian.net/browse/ECPC-144 | [5 empty] | Done 18.06.24
|  | Verify Company Reference Id |  |  |  |  | Remaining to check
|  | Verify email Id format |  |  |  |  | pass
|  | Verify contact should be 10 digits. |  | 2313123113 8787878756 0000000000 | It should not be allowed more than 10 digits |  | pass
|  | Verify validation message for Company contact number |  | 2313123113 8787878756 0000000000 |  | Please enter a valid phone number | pass
|  | Verify characters and special characters are not allowed in phone |  |  | should not be allowed | As per expected result | pass
|  | Verify GST number |  |  | It should be 15 digits. Not allowing more than 15 digit. |  | pass
|  | Verify only digits and characters not allowing that means a combination of characters and digits should be allowed. |  |  |  |  | pass
|  | Verify GST format |  |  | First two - Digits Three to Seven - Characters Eight to eleven - Digits Twelve - Characters Thirteen digit Fourteen character Fifteen - Digit Ex. 29GHTYG8786S1Z5 |  | Pass
|  | Verify validation message check in GST |  |  | It should be "Not matched with the valid schema, ensure that the GST number is in uppercase" | "Not matched with the valid schema, ensure that the number is in uppercase" | pass | https://cuneiform.atlassian.net/browse/ECPC-145 | [5 empty] | Done 18.06.24
|  | Verify drop box of Buyers and Suppliers |  |  |  |  | pass
|  | Verify Pincode |  |  | It should be 6 digits |  | pass
|  | Verify characters should not be allowed in pincode field |  |  |  |  | pass
|  | Verify after enter pincode, city and state should be fetched |  |  |  |  | pass
|  | Verify when wrong Pin code enters |  | 312312 | Not a valid Pincode | Message comes like "Not a valid Pincode" but it comes five to six time. Please refer screenshot. | Pass | https://cuneiform.atlassian.net/browse/ECPC-148 | 1.3
|  | Verify save button functionality |  |  |  |  | pass
| Add Multiple Buyers/Suppliers | Verify path of title Upload File/Verify Header/Verify Data/Finish |  |  |  |  | pass
|  | Verify UI for Add Multiple Buyers |  |  |  |  | Pass
| Add Multiple Companies Pop UP | Verify download Excel Template |  |  | An Excel sheet should be downloaded | When we download the Excel template, the txt file is downloaded. The downloaded format comes incorrect. | Pass | https://cuneiform.atlassian.net/browse/ECPC-149 | [5 empty] | Assign back | Assign back 04.07.24 | Done 30.08.24
|  | Verify drag and drop excel file |  |  |  |  | pass
|  | Verify save button work |  |  |  |  | pass
| Delete Buyers/Suppliers | Verify delete buyers button functionality |  |  |  |  | pass
|  | Verify delete Supplier button functionality |  |  |  |  | pass
|  | Verify delete button functionality |  |  | When we click on the delete button message popup comes. It displays messages like "Are you sure about deleting XYZ Company?" you won't be able to revert this. ................................................................ Please update the message below: "Are you sure about deleting XYZ Company". You won't be able to revert this. | Are you sure about deleting XYZ Company?" you won't be able to revert this. | Pass | https://cuneiform.atlassian.net/browse/ECPC-154 | [5 empty] | Assign back for new updation You have done this but could u pls set the format as below if possible Are you sure about deleting SRV Pvt Ltd? You won’t be able to revert this! In the second line full company name should come,
|  | Verify validation message of delete button |  |  |  | XYZ company deleted successfully | pass
|  | Verify cancel button functionality |  |  |  |  | pass
EditBuyers/Suppliers Details
| Edit Buyers/Suppliers Information | All information should be editable |  |  |  |  | pass
|  | Verify UI for Edit Buyers/Suppliers Details |  |  |  |  | pass
|  | Verify path below Buyers and Suppliers details |  |  |  |  | pass
|  | Verify change logo button |  |  | The change logo button should be there for uploading the business logo. | Change logo button missing | Pass
|  | Verify Edit mode-when it is in edit mode then title should be Buyers and Suppliers Edit |  |  |  | Buyers and suppliers Details | Remaining to check
| Personal Information | Verify title of edit Information like Full Name / Email Id / Contact Number |  |  |  |  | pass
|  | Verify validation message of Full name-Max characters |  |  |  | Name must be less than 80 characters | pass
|  | Verify validation message of Full name-Min characters |  |  |  | Name must be at least 3 characters long | pass
|  | Verify phone number should be 10 digits |  |  | Phone number should be 10 digits | As per Expected Result | pass
|  | Verify characters and special symbols are not allowed |  |  |  |  | pass
| Company Information | Verify title of "Company details" |  |  | "Company details" title should be in edit mode table same as Personal Info | "Company Details" title is missing in edit mode When we click on the anyone of buyer/supplier and clickon edit button, at that time only "Personal Information" title is there but "Company Details" title is not there . When we add the records at that time both titles are available. | pass | https://cuneiform.atlassian.net/browse/ECPC-155 | [5 empty] | Same issue Done | Done 05.06.24
|  | Verify text like Name of Company / Official Company Email ID/Company Contact Number/GST Number |  |  |  |  | pass
|  | Verify company name is minimum 3 and maximum 80 characters |  |  |  |  | pass
|  | Verify validation message of Email Id |  |  | It should be "Invalid email address". | Enter a valid Email, Please! | pass
|  | Verify Company contact number should be 10 digits |  |  | Phone number should be 10 digits. | As per Expected Result | pass
|  | Verify characters and special symbols are not allowed in company contact number |  |  |  |  | pass
|  | Verify GST number has a limit of 15 characters. The combination of Digits and characters should allowed. Only digit or only character should not be allowed |  | 424234242424242 jgjhgjhgjgjgjgj 27AAAAP0267H2ZN |  | "Not matched with the valid schema, ensure that the number is in uppercase" | pass
|  | Verify save button work |  |  |  |  | pass
| Billing Address | Verify title like Name/Email/Contact Number/Location Address/Location Address/Pincode/City/State/Country |  |  | It should be Full Name/Email/Contact Number/Location Address 1/Location Address 2/ Pincode/City/State/Country Please update as above. |  | pass | https://cuneiform.atlassian.net/browse/ECPC-156 | [5 empty] | Done 18.06.24
| Warehouse Locations - Add | Verify name is minimum 3 and maximum 80 characters. |  |  |  |  | pass
|  | Verify UI of Warehouse add |  |  |  |  | pass
|  | Verify validation message of Full name-Min characters in Warehouse Locations |  |  | it should be "Name must be at least 3 characters long" | Name must be at least 3 characters long | pass
|  | Verify validation message of Full name-Max characters in Warehouse Locations |  |  | It should be "Full Name must be less than 80 characters. Please update it. | Name must be less then 80 characters | pass | https://cuneiform.atlassian.net/browse/ECPC-157 | [5 empty] | Done 18.06.24
|  | Verify validation message of Email Id |  |  | It should be "Invalid email address" . | Complete email address | pass | https://cuneiform.atlassian.net/browse/ECPC-158 | [5 empty] | Done 18.06.24
|  | Verify phone number should be 10 digits |  |  | Phone number should be 10 digits | As per Expected Result | pass
|  | Verify characters and special symbols are not allowed |  |  |  |  | pass
|  | Verify Location address 1 first word capitalize |  | shreepad app | First letter should be capital automatically when user enter | location address 1 first letter comes with small letter. Ex. Shreepad | pass | https://cuneiform.atlassian.net/browse/ECPC-159 | [5 empty] | Done 18.06.24
|  | Verify Location address 2 first word capitalize |  | bhairavnath | First letter should be capital automatically when user enter | location address 2 first letter comes with small letter. Ex. bhairavnath | pass | https://cuneiform.atlassian.net/browse/ECPC-160 | [5 empty] | Done 18.06.24
|  | Verify validation message of location address 1 for Min characters in Warehouse Location |  |  | It should be "Address must be less than 150 characters. | Address name must be less than 150 characters | pass | https://cuneiform.atlassian.net/browse/ECPC-161 | [5 empty] | Done 18.06.24
|  | Verify validation message of location address 1 for Max characters in warehouse Location |  |  | It should be "Address must be at least 3 characters long. | As per Expected Result | pass
|  | Verify validation message of location address 2 for Min characters in warehouse Location |  |  | It should be "Address must be less than 150 characters. | Address name must be less than 150 characters | pass | https://cuneiform.atlassian.net/browse/ECPC-162 | [5 empty] | Done 18.06.24
|  | Verify validation message of location address 2 for Max characters in warehouse Location |  |  | It should be "Address must be at least 3 characters long. | As per Expected Result | pass
|  | Verify Pincode |  | 370001 | it should be 6 digits and character and special character not allows | As per Expected Result | pass
|  | Verify validation message of Pincode |  | 312312 | Not a valid Pincode | Message comes like "Not a valid Pincode" but it comes five to six time. Please refer screenshot. | pass | https://cuneiform.atlassian.net/browse/ECPC-163 | 1.5 |  |  |  |  | Done 18.06.24
|  | Verify address updated with the use of edit button |  |  | Address should be updated only primary email address should not be updated | As per Expected Result | pass
|  | Address format |  |  | It should be below : 23123123, Ghfhfhfhhf, Ahmedabad - 382481, Gujarat Gap should be before and after "-". All first letter is capital when user enter Location 1 and 2 | 23123123, ghfhfhfhhf, Ahmedabad- 382481, Gujarat- India | pass | https://cuneiform.atlassian.net/browse/ECPC-164 | [5 empty] | Done 18.06.24
| Warehouse-Delete Address | Verify delete button functionality |  |  | When we click on delete button, one pop up should be come | As per Expected Result | pass
|  | Verify cancel button functionality |  |  |  |  | pass
|  | Verify delete address |  |  | Primary address should not be deleted | can not delete primary address | pass
|  | Verify Primary address delete |  |  | It should not be delated |  | pass
| Delivery/Shipping-Edit Address | Verify all information editable |  |  |  |  | pass
| Delivery/Shipping Locations-Add | Verify title like Name/Email/Contact Number/Location Address/Location Address/Pincode/City/State/Country |  |  | It should be Full Name/Email/Contact Number/Location Address 1/Location Address 2/Pincode/City/State/Country |  | pass | https://cuneiform.atlassian.net/browse/ECPC-165 | [5 empty] | Done 18.06.24
|  | Verify validation message of Min characters of Full name |  |  | it should be "Name must be at least 3 characters long" | Name must be at least 3 characters long | pass
|  | Verify validation message of Max characters of Full name |  |  | It should be "Full Name must be less than 80 characters. Please update it. | Name must be less then 80 characters | pass | https://cuneiform.atlassian.net/browse/ECPC-166 | [5 empty] | Done 18.06.24
|  | Verify validation message of Email Id |  |  | It should be "Enter a valid email, please!". | Enter a valid email, please! | pass
|  | Verify validation message of Min characters of Location address 1 |  |  | It should be "Address must be at least 3 characters long" | As per Expected Result | pass
|  | Verify validation message of Max characters of Location Address 1 |  |  | It should be "Address must be less than 80 characters. Please update it. | Address name must be less than 150 characters. | pass | https://cuneiform.atlassian.net/browse/ECPC-167 | [5 empty] | Done 18.06.24
|  | Verify validation message of Min characters of Location address 2 |  |  | It should be "Address must be at least 3 characters long" | As per Expected Result | pass
|  | Verify validation message of Max characters of Location Address 2 |  |  | It should be "Address must be less than 80 characters. Please update it. | Address name must be less than 150 characters. | pass | https://cuneiform.atlassian.net/browse/ECPC-168 | [5 empty] | Done 18.06.24
|  | Verify pincode |  | 370001 | It should be 6 digits and character and special character not allows | As per Expected Result | pass
|  | Verify validation message of Pincode |  | 312312 | Message should be came when user enter wrong password But here message comes five to six time. It should not. Please refer screenshot. | Message comes like "Not a valid Pincode" | pass | https://cuneiform.atlassian.net/browse/ECPC-169 | 1.6 |  |  |  |  | Done 18.06.24
|  | Verify City/State/Country should be fetched by pincode |  |  |  |  | pass
|  | Verify address format |  |  | It should be Rohan Shree apt, Solabhagawat, Ahmedabad - 382481, Gujarat - India. Format should be as below Name Address1/2 City-Pin, State-Country And Space comes after comma. | Rohan shree apt,solabhagawat,Ahmedabad - 382481, Gujarat - India | pass | https://cuneiform.atlassian.net/browse/ECPC-170 | 1.7 |  |  |  |  | Done 18.06.24
| Delivery/Shipping Locations-Edit | Verify all data updated successfully |  |  |  |  | pass
| Delivery/Shipping Locations-Delete | Verify delete functionality |  |  |  |  | pass
|  | Verify Main Delete button functionality |  |  |  |  | pass
|  | Verify cancel button functionality |  |  |  |  | pass
| Company Balance | Verify company balance like Date/Payable/Receivable/Supply/Return |  |  |  |  | pass
|  | Verify company balance details |  |  |  |  | Remaining to check
| Edit and Add Buyer and Sellers | Verify Buyers and Sellers should be same. |  |  | It should be as below: Personal Info Full Name Phone Email Id Company Details: Name Of Company Company Reference Id Official Email Address Company Contact Number GST Number Company Type Rest are ok in both | Here the title of edit of Buyers and Suppliers are as below : Personal Info Full Name Email Id Contact Number Name Of Company Official Company Email ID Company Contact Number GST Number Here some fields are not available like Company Reference Id and Company Type. It should be available in Edit option. | Pass | https://cuneiform.atlassian.net/browse/ECPC-239 | [5 empty] | Not Done all emails should contain domain @poonamcoatings.com while login, other domains will not get accepted according to new logic, and also google login will not be there---By prateek this is major change . and has been kept on hold from prateek’s side...By umang
|  | Error message comes when duplication occur |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-240 | 2.5 |  |  |  |  | Done 14.06.24
Phase -II Testing
07.08.24 | Buyers and Suppliers-Main pannel | [5 empty] | pass
| Search | Search button functionality | Search button functionality |  |  |  | pass
| Filter button | Filter button work |  |  |  |  | pass
| View button | View button functionality |  |  |  |  | pass
| Delete button | Delete button functionality work |  |  |  |  | pass
| Date of creation | Verify the date of record added- Existing date will be seen |  |  |  |  | pass
| Verify delete all record button functionality | All record deleted successfully |  |  |  |  | pass
| Add record | When we add record and deleted it, after that when we are trying to add this same record then it displays en error like "Company is already Exist". However, we can not see the record in the list. After deleted record database shoul be refreshed. |  |  |  |  | Pass | [6 empty] | "14.08.24 Now it is resolved"
| Credit limit | Credit limit should be in digit only |  |  |  |  | pass
| Pay Duration | Pay duration in day - it should be in digits |  |  |  |  | pass
| Pegination | Check pegination |  |  |  |  | pass
| Edit Buyers and Supplier | when we edit the buyer and supplier at that time in Full name digit is allowed to be entered, whereas in add Buyers and Suppliyer We have not given this facility. So in this, strict validation should be there for not allowing digits to be entered. However, validation message comes and not allowing to enter digits |  |  |  |  | Pass |  | 2.1 |  |  | Done |  | Done
|  | One company should have unique GST Here I have tried to create two company with same GST and it is allowed to be added. But it should not allowed to be entered |  |  |  |  | Pass |  | 2.3 |  |  | Done |  | "Done 30.08.24"
|  | When we are trying to edit the name of company, one validation message comes like "input must be a 24 character hex string byte unit 8 array or an integer. User can not understand this validation message comes for which field. Pls update the validation message |  |  |  |  | Pass |  | 2.2 |  |  | Done | Done But Not Deployed | "Not Done Assign back 30.08.24" | Done 05.09.24
|  | We have to set limit in Pay duration in a day for 360/365 days. So, we can prevent debt from carrying over into the following year." We also talk with client how many days that client wants to set. Here it takes value like - 303423423423 Needs to implement in add and edit module. |  |  |  |  | Pass |  |  |  |  | Done |  | Done 30.08.24 | 05.09.24
|  | Verify GST number edit functionality |  |  |  |  | pass
|  | Verify name of company |  |  |  |  | pass
|  | Special character and character not allowing in credit and duration of days |  |  |  |  | pass
| Sales Person Info | Verify Edit sales person name |  |  |  |  | pass
|  | "One button should be there for the selection of number of pages like 15/25/30 pages etc. So, user can navigate easily. If a user is on page no 275 then how can they navigate on 50 page. They have to click one by one page and reachout on 50 page no" |  |  |  |  | Keep in CR |  |  |  |  | Will be done later if asked by client. |  | Ok , It will be puts in CR
| Add Bulk Upload data | Download excel file function is working. But when we download the sheet, sheet is filled with data It should be blank. Additionally, the fields in the sheet differ from those in the 'Add Single Company' field of the form. Both fields should be the same to maintain uniformity." |  |  |  |  | Fail |  |  |  |  | data shown in template is dummy data for 9 types of record . there are only 9 dummy data | data shown in template is dummy data for 9 types of record . there are only 9 dummy data | "Discussed with Dev. Kinjal Leuva record is not saved Pls change excel file. Also pls remove dummy field . U can give one for example but it will be blured"
|  | "When we upload the Excel sheet, a message appears saying 'Successfully uploaded all the companies,' but the data is not added or saved." |  |  |  |  | Fail |  |  |  |  | we verified data is added | New 30.08.24 | Not Done 05.09.24
|  | When we click on View at that time null coming in most of the rows like Fullname/email/contact num etc |  |  |  |  | pass |  |  |  |  | Done But Not Deployed |  | Done 05.09.24

## User Management
DATE OF CREATION | 02.05.24..10.05.24 |  |  |  |  | TOTAL PASS | 38
MODULE NAME | User Management |  |  |  |  | TOTAL FAIL | 15
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 53
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Actual Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Developer Comment 1 | Developer Comment 2 | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
| Header-Search bar | Verify search button functionality |  |  | Search button is not required on header |  | pass | https://cuneiform.atlassian.net/browse/ECPC-172 |  |  |  |  | Done 18.06.24
|  | Verify Notifications |  |  |  |  | Remaining to check
|  | Verify Profile should be redirect to profile page |  |  |  |  | pass
|  | Verify logout button functionality |  |  |  |  | pass
| UMS | Verify field like User Name / Position / Status / Action |  |  | It should be User Name / Position /Phone Number / Status / Action The phone number should be there so that the admin can view it. In the future if two users have the same name and the number is different then the admin can view it. | Here Phone number is not there . | pass | https://cuneiform.atlassian.net/browse/ECPC-173 |  |  |  |  | Done 18.06.24
| Add User | Verify Search user | 1) Click on Search bar 2) Type which u want to search | Amit | Records should be searched exact with the input | As per expected result | pass
|  | Verify Field like First Name/Last Name/Email ID/Phone Number/Gender/DOB/Select Role/Select Department |  |  |  |  | pass
|  | Verify first letter should be capitalize when user enters First Name and Last Name |  |  |  |  | pass
|  | Verify Min character of First name and Last Name |  |  |  | First name must be at least 3 characters long. Last name must be at least 3 characters long. | pass
|  | Verify Max characters allow in First Name and Last Name |  |  | It should be as below: 1) First name must be less than 80 characters. 2) Last name must be less than 80 characters. Please update as above. | 1) First name must be less then 80 characters. 2) Last name must be less then 80 characters. | pass | https://cuneiform.atlassian.net/browse/ECPC-174 |  |  |  |  | Done 18.06.24
|  | Verify Email id format |  |  |  |  | pass
|  | Verify validation message of email address |  | test@.com text@com 123@gmail.com | It should be "Invalid email address". Also when user hover on text box of email address then one message displayed for its format. Check screenshot | Complete email address Please update with "Invalid email address" | pass | https://cuneiform.atlassian.net/browse/ECPC-175 |  |  |  |  | Done 18.06.24
|  | Verify dropbox list of Gender like Male/Female/Other |  |  | It should be selected |  | pass
|  | Verify date format |  | 08.05.275760 | It should be DD-MM-YYYY Please refer screenshot However the validation message came and date not saved but it should be strict validation to entering year in four digits. | Here date format is dd.mm.yyyyyy | pass | https://cuneiform.atlassian.net/browse/ECPC-176 | 1.8 |  |  |  | Done 18.06.24
|  | Verify old date should not be accepted |  | 02.04.1800 | The year should be fixed after by 1900, it will be allow to enter. Before 1900 should be blocked. | Allowed to enter 02.04.1800 | pass | https://cuneiform.atlassian.net/browse/ECPC-177 | 1.9 |  |  |  | Done 18.06.24
|  | Verify characters not allow in date |  |  |  |  | pass
|  | Verify Select Role from dropbox list like Admin/Manager |  |  |  |  | pass
|  | Verify selection of department |  |  |  |  | pass
|  | Verify without selecting privileges |  |  | It should throw error without selecting privileges | Privileges required | pass
|  | Verify duplicate record not allow | 1) Click on User Management 2) Click on Add New 3) Fill details as below : First Name LastName Email Id Phone Number Gender DOB Select Role Select Department 4) Add Privileges 5) Click on Submit | 1) Rahul 2) Patel 3) rp6038272@gmail.com 4) 7016248248 5) Female 6) 02.12.2000 7) Admin 8) Administrator | It should not allow to enter duplicate data | Phone number is already taken Email is already taken | Pass
|  | Verify status |  |  |  |  | Remaining to check
| View User | Verify Action button view button work |  |  | View button should be there | It is missing. If it is possible then pls add it | pass | https://cuneiform.atlassian.net/browse/ECPC-178 | 2 |  |  |  | Done 18.06.24
|  | Verify new user add | 1) Click on User Management 2) Click on Add New 3) Fill details as below : First Name LastName Email Id Phone Number Gender DOB Select Role Select Department 4) Add Privileges 5) Click on Submit | 1) Rahul 2) Patel 3) rp6038272@gmail.com 4) 7016248248 5) Female 6) 02.12.2000 7) Admin 8) Administrator Add privileges |  |  | pass
| Edit Profile | Verify title of First Name/Last Name/Email Id/Phone Number/Gender/Date of Birth/Select role/Select Department |  |  |  |  | pass
|  | Verify First name and last name have limit of character i.e max-80 characters |  |  |  |  | pass
|  | Verify First name and last name have limit of character i.e min-3 characters |  |  |  |  | pass
|  | Verify validation msg of Min characters of First name and Last Name |  |  | It should be "First Name must be at least 3 characters long." "Last Name must be at least 3 characters long. Please update as below: "First Name must be at least 3 characters long." | Name must be at least 3 characters long. Last name must be at least 3 characters long. | pass | https://cuneiform.atlassian.net/browse/ECPC-179 |  |  |  |  | Done 18.06.24
|  | Verify validation msg of Max characters of First name and Last Name |  |  | It should be as below : 1) First Name must be less than 80 characters. 2) Last Name must be less than 80 characters. Please update as above. | 1) First name must be less then 80 characters. 2) Last name must be less then 80 characters. | pass | https://cuneiform.atlassian.net/browse/ECPC-180 |  |  |  |  | Done 18.06.24
|  | Verify First name, last name should not allow digits |  |  | digit should not be allowed to enter |  | pass
|  | Verify Email id format |  |  | When user not enter "@"validation message should be came | As per expected result | pass
|  | Verify validation message for email address |  | test@.com text@com 123@gmail.com | It should be "Invalid Email Address". Also when user hover on text box of email address then one message should be displayed for its format. Check screenshot | Complete email address Please update "Invalid Email Address" | pass | https://cuneiform.atlassian.net/browse/ECPC-181 | 1.2 |  |  |  | Done but toolkit not comes after hover Done 04.07.24
|  | Verify Phone number should be 10 digits |  |  |  |  | pass
|  | Verify edit Gender like Male/Female/Others should be selected |  |  | User able to edit any one option from the dropdown |  | pass
|  | Verify date format |  | 08.05.877650 | It should be DD-MM-YYYY Please refer screenshot However the validation message came and date not saved but it should be strict validation to entering year in four digits. | Here date format is dd.mm.yyyyyy | pass | https://cuneiform.atlassian.net/browse/ECPC-182 | 2.1 |  |  |  | Done 18.06.24
|  | Verify old date should not be accepted |  | 02.04.1800 | The year should be fixed after yr. 1900.Only accepts dates from the year 1900 and later. Before 1900 should be blocked. | Allowed to enter 02.04.1800 | pass | https://cuneiform.atlassian.net/browse/ECPC-184 |  |  |  |  | Done 18.06.24
|  | Verify edit role from dropdown |  |  |  |  | pass
|  | Verify edit department from the dropdown |  |  |  |  | pass
|  | Verify submit button functionality |  |  |  |  | pass
|  | User Update detail successfully | 1) Click on User Management 2) Select any one record 2) Click on edit button 3) update details as below : First Name LastName Email Id Phone Number Gender DOB Select Role Select Department 4) update Edit Privileges 5) Click on Submit | 1) Rahul 2) Patel 3) rp6038272@gmail.com 4) 7016248248 5) Female 6) 02.12.2000 7) Admin 8) Administrator Add privileges |  | User details updated successfully | pass
| Add Privileges | Verify after select the privilege, user access accordingly |  |  | Given rights for only read-User Management | User list read for User Management | pass
|  | Verify if the privileges not given to user he/she unable to access module |  |  |  | Don’t allow to access | pass
|  | Verify privileges for User Management/Email Management/Buyers and Suppliers Management /Calendar Management/Department Management/ Company Management/Sales Purchase Management/Inventory Management/ Payment Management/Report Intellegence Management/ResourcePlanning Management/ Account Tally Management |  |  |  |  | pass
|  | Verify the UI and text of privileges popup |  |  |  |  | pass
|  | Verify Submit button work |  |  |  |  | pass
| Delete Profile | Verify delete button functionality | 1) Click on User Management 2) Select any one record 2) Click on delete action button 3) Click on Delete |  | It should be Are you sure about deleting Ron? You won't be able to revert this! Please update as above. | Are you sure about deleting Ron? you won't be able to revert this! Ron deleted successfully | pass | https://cuneiform.atlassian.net/browse/ECPC-187 |  |  |  |  | Done 18.06.24
|  | Verify cancel button functionality |  |  |  |  | pass
| View Profile | Verify view profile |  |  | View button should be there. |  | pass
|  | Verify pegination |  |  |  |  | pass
|  | After adding record the validation message coming like "Success" |  |  | It should be "User added successfully" |  | pass
| User Management Login | Verify login of particular user |  |  |  |  | pass
|  | Verify Search bar on particular user |  |  |  |  | pass
| View | View button should be there |  |  | When we given rights of read then view action button should be there | View button is not there | pass | https://cuneiform.atlassian.net/browse/ECPC-189 |  |  |  |  | Done 18.06.24
|  | Verify number of manager is possible but admin is only one |  |  | A Number of managers should be allowed to add. Restriction should be done for admin only | Here, when I click role from dropdown in add user, we are unable to add a new manager. One message comes up like "Manager already exists for this department". It should be for admin. A Number of managers should be allowed to add. | pass | https://cuneiform.atlassian.net/browse/ECPC-190 | 2.2 |  |  |  | Need to ask done by devloper
|  | Verify Phone should be in user management list |  |  | User Name / Phone Number / Position / Status / Action , titles there. So, that admin can easily contact to seller or buyer. | Here User Name/Position/Status/Action titles there . | pass | https://cuneiform.atlassian.net/browse/ECPC-225 | 2.4 |  |  |  | Done 18.06.24
| Remaining | Verify all Email Id accepted in user add |  |  | All Id should be accepted. Only yopmail id user added gmail id user not allow. | Here when user added with gmail id then it is not allowed to add. Only yopmail id user allows to be added | pass | https://cuneiform.atlassian.net/browse/ECPC-226 |  |  |  |  | Done 18.06.24
| Add User | Validation message of email id check |  |  | It should be "Email must contain@poonamcoatings.com domain" | email must contain@poonamcoatings.com domain | pass | [5 empty] | New 18.06.24
Phase -II Testing
10.08.24 | User Management list | User Management list - Department column should be added so that client easily see that user belongs to which department along with their position |  |  |  |  | Pass |  | 3.1 |  | Done |  | Done 30.08.24
| User login | [5 empty] | pass |  |  |  | Not clear. user is getting logged in |  | Pls Ignore it, it is blank
|  | Only an admin should be able to assign the role of admin to any user. To protect certain functions, ensure that only authorized users (admins) are permitted to perform them. Here user can able to assign the role of admin to any user. |  |  |  |  | fail |  |  |  | One who has privilages can assign the roles to other user with admin permissions |  | Need to discuss with team | No need to do for now 05.09.24
|  | "View button" functionality not works in user list-When we loggedin with other user. With the credential of admin , view button is working |  |  |  |  | pass |  | 3.2 |  | if he has privilages to view the user details he can view the details |  | "You r not getting my point. With the specific user credential View option is not working. Even the View rights is already given. But for now it is working."
| Action button UI | "Active User - It should be in green color background image Deactivate User - It should be in red color background image Here, it is the opposite of it . Please make the changes because the inactive user status comes in red color so, inactive user action button should be also in red color" |  |  |  |  | Pass |  | 3.3 |  |  | Change if necessary | "Not Done 30.08.24" | No need to do for now 05.09.24
| Privileges | To avoid user confusion, we should temporarily hide some privileges that are not currently being used in ERP. Specifically, the following features should be hidden: 1) Reports Intelligence Management 2) Resource Planning Management 3) Account Tally Management 4) Configuration Management 5) Payment Management |  |  |  |  | pass |  |  |  |  | Done But not deployed | Not Done 30.08.24 | Done 05.09.23
|  | When we edit DOB and tried to loggedin at that time New Dob 's year for password was not accepted. Only first time entered year is accepted as in password . Example. Here I have entered DOB 02.12.1995 and edited this date with 02.12.1994 . When I tried to login with "Ronak@1994" then loggedin was not successfull. |  |  |  |  | pass |  | 3.4 |  |  | Done But not deployed | Not Done 30.08.24 | Will check later Sometimes it is work sometimes not work Now it is work
|  | When I was given rights of company module to any user and after logged in, click to "Company Module" then 404 Error comes and redirected on login page |  |  |  |  | pass |  |  |  |  | it's happening because only super admin has permission to open company tab | Not Done - 14.08.24 Not Done - 30.08.24 | If the rights given to only admin then we have to block the company management option to the user | Done 05.09.24
|  | After logged in with correct credential, user unable to login sometime , already discussed with Dev. Umang |  |  |  |  | Pass | [6 empty] | Not Done 30.08.24 | Done 05.09.24
|  | Verify user logged in and given rights of view/read |  |  |  |  | Pass
|  | Verify user logged in and given rights of write |  |  |  |  | pass
|  | Verify user logged in and given rights of delete |  |  |  |  | pass
|  | Edit the user data with the field which is already created |  |  |  |  | pass
|  | Verify sameuser name with same DOB allowed user to login because of email address is different check validation is given |  |  |  |  | pass
|  | I have logged in with user name Pre pretest@poonamcoatings.com Pre@2002 It couldn't able to logged in . Discussed with Dev. Prateek Mishra |  |  |  |  | Fail

## Profile Management
DATE OF CREATION | 24.04.24 |  |  |  |  | TOTAL PASS | 22
MODULE NAME | Profile Management |  |  |  |  | TOTAL FAIL | 9
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 31
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Actual Result | Status | JIRA Ticket ID# | Screenshot | Deigner Bug | Designer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
24.04.24 | My Profile-Edit | Verify search button |  |  | Search button is not required on header |  | pass | https://cuneiform.atlassian.net/browse/ECPC-192 |  |  |  | Done 18.06.24 |  | Done
|  | Verify Notifications |  |  | Notification comes after new alert |  | Remaining to check
|  | Verify Profile should be redirect to profile page |  |  | Should be allowed webP,JPEG,GIF,Png. Not allows pdf | As per expected result | pass | [6 empty] | Done
|  | Verify logout button functionality |  |  |  |  | pass | [6 empty] | Done
|  | Verify change Profile Pic button functionality |  |  | It should be allowed to change the profile pic of user | Profile picture updated successfully | pass | [6 empty] | Done
| Personal Information | Verify details like First Name/Last Name/Phone Number/Email ID |  |  | All fields name should come with Propercase |  | pass | [6 empty] | Done
| Edit Info | Verify save button functionality when user not fills details |  |  | Validation message should be come for all field | As per expected result | pass | [6 empty] | Done
|  | Verify Min characters of First name and Last Name |  |  | It should be "First Name must be at least 3 characters long." "Last Name must be at least 3 characters long. Please update as above: | "Name must be at least 3 characters long." "Name must be at least 3 characters long." | pass | https://cuneiform.atlassian.net/browse/ECPC-193 |  |  |  | Done 18.06.24 |  | Done
|  | Verify Max characters of First name and Last Name |  |  | It should be as below : 1) First name must be less than 80 characters. 2) Last name must be less than 80 characters. Please update as above. | 1) First name must be less then 80 characters. 2) Last name must be less then 80 characters. | pass | https://cuneiform.atlassian.net/browse/ECPC-194 |  |  |  | Done 18.06.24 |  | Done
|  | Verify when user enter inofomations, first letter of the word should be came capitalize automatically in First Name and Last Name |  | Ex. Sachin Patel sachin.patel@gmail.com 7664566578 | First name Last name first letter should be came in capital | As per expected result | pass | [6 empty] | Done
|  | Verify First name last name allow digit or not |  |  | digits should not be allowed to enter |  | pass | [6 empty] | Done
|  | Verify edit phone number |  |  | It should not be allowed more than 10 digits. |  | pass | [6 empty] | Done
|  | Verify edit email Id |  |  |  |  | pass | [6 empty] | Done
|  | Verify validation message for edit email address |  | test@.com text@com 123@gmail.com |  | Enter a valid email, please! | pass | [6 empty] | Done
|  | Verify Gender like Male/Female/Others should be selected |  |  | User able any one option from the dropdown |  | pass | [6 empty] | Done
|  | Verify date format |  | 08.05.877650 | It should be DD-MM-YYYY Please refer screenshot However the validation message came and date not saved but it should be strict validation to entering year in four digits. | Here date format is dd.mm.yyyyyy | pass | https://cuneiform.atlassian.net/browse/ECPC-195 |  |  |  | Done 18.06.24 |  | Done
|  | Verify old date should not be accepted |  |  | The year should be fixed after by 1900, it will be allow to enter. Before 1900 should be blocked. |  | pass | https://cuneiform.atlassian.net/browse/ECPC-196 |  |  |  | Done 18.06.24 |  | Done
|  | Verify save button functionality | Personal Inofrmation 1) Click on Settings 2) Click on Profile 3) Click on Edit button of personal info. 4) Edit information which you want like : First Name Last Name Phone Email Gender DOB | Anitd Joshij 999999999999 admin@poonamcoatings.com Male 01.04.1999 | Personal information should be saved | User details updated successfully | pass | [6 empty] | Done
|  | Verify validation message for save personal information |  |  | Validation message should be like : "Personal Information updated successfully" | User details updated successfully | pass | [6 empty] | Done
| Change Password | Verify details like Current Password/New Password/Re-Enter New Password |  |  |  |  | pass | [6 empty] | Done
|  | Verify Eye button |  |  | Eye button should be there in Current Password/New Password/Re-Enter New Password So, at the time of change the password, user can view their input. | There are no any eye buttons available | Pass | https://cuneiform.atlassian.net/browse/ECPC-197 |  |  |  | Not assigned to me |  | Done 30.08.24
|  | Verify title of Current password, Password and Confirm Password | 1) Click on Setting then Change Password 2) Click on Edit button 3) Enter Current Password 4) Enter New Password 5) Enter Confirm Password 7) Click on Save button | Super@1234 Super@123 Super@123 | Title should be as below: Current Password New Password Confirm Password | Current Password Password Confirm Password | pass | https://cuneiform.atlassian.net/browse/ECPC-198 |  |  |  | Done 18.06.24 |  | Done
|  | Verify Current password and New password both should be different |  |  |  |  | pass
|  | Verify message comes at the time of changing password |  |  | The validation message should be as below: "New Password should be different from the current password". | New Password should be different from old Password | Pass | https://cuneiform.atlassian.net/browse/ECPC-199 |  |  |  | Assign back 18.06.24 |  | Done 30.08.24
|  | Verify validation message check for confirm password |  |  | It should be "Confirm password does not match" | When we enter new password and confirm password at that time validation lessage comes like " Confirm passwords does not match" | pass | https://cuneiform.atlassian.net/browse/ECPC-200 |  |  |  | Done 18.06.24 |  | Done
|  | Verify New password and Confirm Password both should be same | Personal Information 1) Click on Settings 2) Click on Profile 3) Click on Edit from Change Password 4) Enter CurrentPassword 5) Enter New Password 6) Enter Confirm Password 7) Click on Save button | Super@123 Super@1234 Super@1234 |  |  | pass | [6 empty] | Done
|  | Verify New password and Confirm Password both should not be same | Personal Information 1) Click on Settings 2) Click on Profile 3) Click on Edit from Change Password 4) Enter Current Password 5) Enter New Password 6) Enter Confirm Password 7) Click on Save button | Super@123 Super@1234 Super@123 | Error should be came if passowrd not match | Confirmed password does not match | pass | [6 empty] | Done
|  | Verify space is not allowed |  |  |  |  | pass | [6 empty] | Done
|  | Verify edit button work |  |  |  |  | pass | [6 empty] | Done
|  | Verify all data should be saved with the use of save button |  |  |  |  | pass | [6 empty] | Done
|  | Verify change password successful | Personal Information 1) Click on Settings 2) Click on Profile 3) Click on Edit from Change Password 4) Enter CurrentPassword 5) Enter New Password 6) Enter Confirm Password 7) Click on Save button | Super@123 Super@1234 Super@1234 | Password should be changed. | Password changed successfully | pass | [6 empty] | Done
Phase - II Testing
09.08.24 |  | All functionality working well checked by automation testing |  |  |  |  | pass | [6 empty] | Done
| Edit Profile | Verify Profile edited successfully |  |  |  |  | pass | [6 empty] | Done
| Edit Password | Verify edit password successfully |  |  |  |  | pass | [6 empty] | Done
|  | Password change - Eye button work different. When eye button crossed-Password should not be seen. And When eye button open then password should be readable. Here functions are opposite |  |  |  |  | Pass |  |  |  |  | Done 30.08.24 |  | Done
|  | Pls update the validation message text "New Password is required" in place of "Password is required" Fail |  |  |  |  | Fail
|  | Please title of DOB same like other title |  |  |  |  | Fail

## Company Management
DATE OF CREATION | 24.04.24 |  |  |  |  | TOTAL PASS | 19
MODULE NAME | Setting - Company Details |  |  |  |  | TOTAL FAIL | 8
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 27
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bugs | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
| Header | Verify search button |  |  | Search button is not required on header |  | pass | https://cuneiform.atlassian.net/browse/ECPC-202 |  |  |  |  | Done | 06.06.24
|  | Verify Notifications |  |  | Notification comes after new alert |  | Remaining to check
|  | Verify Profile should be redirected to profile page |  |  | Should be allowed webP,JPEG,GIF,Png. Should not allowed pdf | As per expected result | pass
|  | Verify logout button functionality |  |  |  |  | pass
| Company Details | Verify titles of company detials like Name of Company/Industry/Founding Year/GST Number/Address Line 1/Address Line 2 /Pincode/City/State/Country/Official Email Address/Contact Number/About Us |  |  |  |  | pass
|  | Verify Min characters of Company name |  |  | It should be "Company Name must be at least 3 characters long." | "Company Name must be at least 3 characters long." | pass
| Edit-Company Details | Verify Max characters of Company name |  |  | It should be as below : 1) Company Name must be less than 80 characters. Please update as above. | 1) Name must be less than 80 characters. | pass | https://cuneiform.atlassian.net/browse/ECPC-203 |  |  |  |  | It is done , but allows 81 characters enter where as the message is for 80 characters max. please update, only 80 characters are allowed to be entered. | 06.06.24 | Done 17.06.24
|  | Verify validation for Industry |  |  | It should be Industry must be less than 3 characters long. Industry must be less than 80 characters. Please update as above. | Industry must be less than 3 characters long. Industy name must be less than 80 characters. | Pass
|  | Verify founding year |  |  | Year should be allowed in 4 digits. i.e 2004(YYYY). It should not be allowed in one digit like 1,5,7 etc | Fere it allows 1, 2,3 etc year | Pass | https://cuneiform.atlassian.net/browse/ECPC-204 |  |  |  |  | Done | 06.06.24
|  | Verify if not entering the year |  |  | It should be "Please enter the year" Valid word is used for the wrong entry here we are not entering anything. | Please enter valid year | Pass | https://cuneiform.atlassian.net/browse/ECPC-205 |  |  |  |  | Done | 06.06.24
|  | Verify GST number digits |  |  |  | It should be 15 alphanumeric | Pass
|  | Verify validation message check in GST |  |  | It should be "Not matched with the valid schema, ensure that the GST number is in uppercase" | "Not matched with the valid schema, ensure that the number is in uppercase" | pass | https://cuneiform.atlassian.net/browse/ECPC-206 |  |  |  |  | Done | 06.06.24
|  | Verify Address - It should be 3 characters minimum address 1 and Address 2 |  |  |  |  | pass
|  | Verify Address - It should be 80 characters for Address 1 and Address 2 max |  |  |  |  | pass
|  | Verify validation message of Address Line 1 , And Address Line 2 for Min characters |  |  | It should be "Address must be at least 3 characters long". | Address must be at least 3 characters long | pass
|  | Verify validation message of Address Line 1 , And Address Line 2 for Max characters |  |  | It should be below : Address line 1 : "Address must be less than 150 characters." Address Line 2: "Address must be less than 150 characters." | In Address line 1: Address name must be less than 150 characters. In Address line 2: Address name must be less than 150 characters. | pass | https://cuneiform.atlassian.net/browse/ECPC-207 |  |  |  |  | Done | 06.06.24
|  | Verify pincode should be 6 digits |  |  |  |  | pass
|  | Verify wrong pincode enters |  |  |  | Enter valid pincode please! | pass
|  | Verify City/State/Country should be fetched by Pincode |  |  |  |  | pass
|  | Verify Official Email Address format |  |  |  |  | pass
|  | Verify not entering email address |  |  |  | Email address should not be empty | pass
|  | Verify validation message for wrong email address |  | test@.com text@com 123@gmail.com | It should be "Invalid Email Address". | Complete email address | pass | https://cuneiform.atlassian.net/browse/ECPC-209 |  |  |  |  | Done | 06.06.24
|  | Verify phone number should be 10 digits max |  |  |  | 10 digit limit fixed | pass
|  | Verify when not entering Phone number |  |  |  | Phone number is required. | pass
|  | verify characters and Special character are not allowed |  |  |  |  | pass
|  | Verify when entering wrong number |  |  |  | please enter a valid number | pass
|  | Verify about Us |  |  | No need of about Us |  | pass | https://cuneiform.atlassian.net/browse/ECPC-210 | [5 empty] | Done 17.06.24
Alignment is not set properly
Phase -II Testing
09.08.24 | Company details
| Add | Verify company details add successfully |  |  |  |  | pass
| Edit | Verify company details edit successfully |  |  |  |  | pass
Warehouse details
| Add | Add warehouse functionality |  |  |  |  | pass
| Edit | Edit warehouse functionality |  |  |  |  | pass
|  | Set as primary functionality |  |  |  |  | pass
|  | Abort functionality |  |  |  |  | pass
| Delete | Delete warehouse address functionality |  |  |  |  | pass
13.09.24 | Comany Manage | Verify Founding year should not more than current year Here I have tried to edit Year 9879. and It not alloweded to be added |  |  |  |  | pass
|  | Verify comapny edit successfully |  |  |  |  | pass
| Bank Details - Add | Verify bank account number should be less than 18 digits |  |  |  |  | pass
|  | Verify IFSC code digits-It should be less than 12 digit means 11 digits should be allowed |  |  |  |  | pass
|  | Verify - In UPI id characters aand digits should be allowed. UPI IDs should not include special characters like *, #, or @ in the part before the "@" symbol, except for dots (.) and hyphens (-), which are permissible. |  |  |  |  | PASS
|  | Verify Account holder name - Specials characters should not be allowed Some banks are providing special characters like Hyphens (-) Apostrophes (') It is depend upon bank so here we are keep this. |  |  |  |  | PASS
|  | Text box size should be fixed when used edit of field of bank then size of text should not be increased as per text contents |  |  |  |  | Fail |  | 4.1
| Bank Details - Edit | All details added successfully |  |  |  |  | PASS
|  | I have added same datails which is already added, here one validation message comes like "Invalid Account number." But it should be : "Account number already exists." |  |  |  |  | Fail |  | 4.2
|  | Verify responsiveness after adding more than 6/7 bank account details. I have added 8 record and checked , here its not comes in the single screen we have scroll it. pls refer screenshot |  |  |  |  | Fail |  | 4.3
| WarehouseAddress-Add | Verify add address successfully |  |  |  |  | PASS
|  | Verify duplicate address should not be allowed to be added |  |  |  |  | PASS
|  | Verify UI of address after adding Added 8 record and checked it is ok |  |  |  |  | PASS
| WarehouseAddress-Edit | Verify edit successfully work |  |  |  |  | PASS
|  | Verify submit button work |  |  |  |  | PASS

## Department Management
DATE OF CREATION | 24.04.24 |  |  |  |  | TOTAL PASS
MODULE NAME | Department Management |  |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 0
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
24.04.24 | Department Management | Verify search button functionality |  |  |  |  | Pass
|  | Verify when we enter only one or two digits for search, Record should be searched and display result |  |  |  |  | pass
|  | Verify Profile button work |  |  |  |  | pass
|  | Verify My profile work |  |  |  |  | Pass
|  | Verify Logout button functionality |  |  |  |  | pass
|  | Verify Notification button functionality |  |  |  |  | Remaining
|  | Verify see more button functionality |  |  |  |  | Remaining
|  | Verify title like Name of Department/Description/Manager/Actions |  |  |  |  | Pass
| Add Button | Verify Add button functionality |  |  |  |  | pass
|  | Verify Abort functionality |  |  |  |  | Pass
|  | Verify limit of character of department name |  |  |  |  | Pass
|  | Verify validation message for Department name |  |  |  | Please enter department first | Pass
|  | Verify validation message for Description when we are not enter anything |  |  | It should be "Description field is required" | please define some characteristics of the department | pass | https://cuneiform.atlassian.net/browse/ECPC-253 |  |  |  |  | Done 27.06.24
|  | Verify validation message for Description |  |  | Message should be "Description must be less than 150 words" | words must be less than 150 words | fail | https://cuneiform.atlassian.net/browse/ECPC-254 |  |  |  |  | Not Done Assign back 27.06.24
|  | Verify validation message for Department Name |  |  |  |  | pass
|  | First letter should be capital in Department name and Description filed |  |  |  | Here In department it takes name's first letter capitalized at the time of entering name. In Description - First letter should be capitalized automatically when user enter description | pass | https://cuneiform.atlassian.net/browse/ECPC-255 |  |  |  |  | Done 27.06.24
|  | Verify department details like "Department Name" and "Description" |  |  |  |  | pass
|  | Verify after click on done button new department should be added |  |  |  |  | pass
|  | Verify not allowing duplicate department | 1) Login 2) Click on Department 3) Click on add 4) Enter Department name 5) Enter Description 6) Click on Submit button | Administration |  | Duplicate records not saved When I entered | pass
| View Button | Verify view button title |  |  | It should be View Department. When we click on edit pen at that time title should be changed. | Edit Department | pass | https://cuneiform.atlassian.net/browse/ECPC-256 |  |  |  |  | Done 27.06.24
|  | Verify in view mode user can only view the department |  |  |  |  | pass
|  | Verify edit button functionality |  |  |  |  | pass
|  | Verify validation message - when we add department at that time one validation message comes |  |  | It should be "Department added successfully" | Department Added successfully | pass | https://cuneiform.atlassian.net/browse/ECPC-257 |  |  |  |  | Done 27.06.24
|  | Verify pegination |  |  |  |  | pass
|  | Verify when we add department, manager fetched |  |  | From where it is fetched |  | pass | https://cuneiform.atlassian.net/browse/ECPC-258 |  |  |  |  | Done 27.06.24
| Delete Button | Verify delete button functionality | 1) Login 2) Click on Department 3) Select any one deaprtment 4) Click on delete button 5) Click on "Delete" |  |  | Department removed successfully | pass
|  | Verify Inner delete button name | 1) Login 2) Click on Department 3) Select any one deaprtment 4) Click on delete button 5) Click on "Yes" |  | When we click on delete button then one "Delete" button is in pop up Delete button name should be "Yes" not Delete |  | pass | https://cuneiform.atlassian.net/browse/ECPC-259 |  |  |  |  | No need to change Done 27.06.24
|  | Verify - Delete multiple data with the use of select all options |  |  | When we click select all option | After selecting "select all" options , "Delete All" button at that time of POP UP comes. POPUP should be in a different color . So that user can aware of that, otherwise all important department will be deleted | pass | https://cuneiform.atlassian.net/browse/ECPC-260 |  |  |  |  | Done 27.06.24
|  | Verify UI of Department list |  |  | Gap seems too much between Name of Department and Description. Please refer Figma |  | fail | https://cuneiform.atlassian.net/browse/ECPC-261 |  |  |  |  | Assign back 27.06.24
Phase -II Testing
10.08.24 | Department details
| Add | Verify Add Department successfully |  |  |  |  | pass
| Edit | Verify Add Department successfully |  |  |  |  | pass
| Delete | Verify Add Department successfully |  |  |  |  | pass
| Abort | Verify abort functionality |  |  |  |  | pass
|  | Pegination check |  |  |  |  | pass
| Filter | Verify filter button work functionality |  |  |  |  | pass
|  | Verify digits are not allowed in Department name |  |  |  |  | pass
|  | Verify manager assigned / Not assigned functionality |  |  |  |  | pass

## Email Management
DATE OF CREATION | 02.05.24 |  |  |  |  | TOTAL PASS
MODULE NAME | Setting - Email Management |  |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 0
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
| Header | Verify search button removed on the header |  |  |  |  | Pass
|  | Verify Profile button functionality |  |  |  |  | pass
|  | Verify Notification button functionality |  |  |  |  | Remaining
|  | Verify search button functionality |  |  |  | Searching successfully | Pass
|  | Verify wrong type in the search bar |  |  |  | Information should not be came | pass
|  | Verify title like Title / Subject / Description |  |  |  |  | Pass
| Add Email | Verify Details like Subject / Title / Description |  |  |  |  | Pass
|  | Verify letter of the title should comes in proper case |  |  |  |  | fail
|  | Verify letter of the subject should come in proper case |  |  |  |  | Pass
|  | Verify Title has limitation of characters to be enter |  |  |  | It should be 80 characters max | pass
|  | Verify subject has limitation of characters to be enter |  |  |  | It should be 80 characters max | pass
|  | Validation message check for max characters in title |  |  |  |  | pass
|  | Validation message check for max characters in subject |  |  |  |  | pass
|  | Title should be come before subject |  |  |  |  | pass
|  | Verify text format in description |  |  |  | All text should be formated with the use of bold, Italic, Numbering, Bullet and paragraph alignment | pass
|  | Verify Save button work |  |  |  | All data should be saved | Pass
|  | Verify after click on cancel button, data should be removed from the list of form |  |  |  |  | Pass
| View button | Verify view button functionality |  |  |  |  | pass
| Edit Email | Verify edit button functionality |  |  |  | Email template details updated successfully | pass
|  | Back button functionality |  |  |  |  | pass
| Delete Email | Verify cancel button work |  |  |  | Cancel the transation | pass
|  | Verify delete button functionality |  |  |  | Email template should be deleted | pass
|  | Verify Delete All button functionality |  |  |  | When u click on "Delete All" button then all selected data deleted. So, sometime user don’t know this functionality. And click it. we have to give some different color in popup or some strong message so, user can aware about this. | fail
|  | Pegination check |  |  |  |  | pass
Phase -II Testing
09.08.24 | Email template | [5 empty] | pass
| Add email template | Veriry add email template functionality |  |  |  |  | pass
| View button | Verify view button functionality |  |  |  |  | pass
| Edit Email | Verify edit button functionality |  |  |  |  | pass
| Delete Email | Verify delete email template successfully |  |  |  |  | pass
|  | Verify back button functionality |  |  |  |  | pass
|  | Verify submit button functionality |  |  |  |  | pass
|  | Verify letter of the title and subject should comes in proper case |  |  |  |  | fail

## Product Catalogue
DATE OF CREATION | 24.04.24 |  |  |  |  | TOTAL PASS
MODULE NAME | Product Catalogue |  |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 0
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
| Brand | Verify Brand title like Name/Actions |  |  | Title should be Brand Name/Actions, Also update the name in Add brand popup |  | pass | https://cuneiform.atlassian.net/browse/ECPC-301 |  |  |  |  | Done 25.06.24
|  | Verify button place |  |  | Back side of color in Delete button icon- light pink color should be slightly dark so it seems in center(Actions). |  | pass | https://cuneiform.atlassian.net/browse/ECPC-295 |  |  |  |  | Done 25.06.24
| Add Brand | Verify title |  |  |  |  | pass
|  | Verify validation message |  |  |  | "Please enter Brand name first" | pass
|  | Submit button work |  |  |  |  | pass
|  | Abort button work |  |  |  |  | pass
| Edit Brand | Verify when u edit product and add same product with the use of edit option , it should decline to be entered |  |  |  |  | pass
|  | Verify edit product |  |  |  |  | pass
|  | Verify abort and submit button work |  |  |  |  | pass
|  | Verify number not allows in brand |  |  |  |  | pass
| Delete Brand | Verify Inner delete button name | 1) Login 2) Click on Setting 3) Click on Product Catalogue 3) Click on Brand 4) Select any one brand 5) Click on delete button 6) Click on "Delete" |  | When we click on delete button then Popup comes, one "Delete" button is there. Delete button name should be "Yes" , not "Delete" Or "Yes Delete" |  | pass | https://cuneiform.atlassian.net/browse/ECPC-296 |  |  |  |  | No need to do
|  | Verify delete button work |  |  |  | Thinner deleted successfully | pass
|  | Check pegination |  |  |  |  | pass
| Categories | Verify Category title |  |  |  |  | Pass
|  | Verify button color |  |  | Back side of color in Delete button icon- light pink color should be slightly dark so it seems in center(Actions) |  | pass | https://cuneiform.atlassian.net/browse/ECPC-297 |  |  |  |  | Done 25.06.24
| Add Product category | Verify title
|  | Verify validation message |  |  |  | "Please enter Product category first" | pass
|  | Submit button work |  |  |  |  | pass
|  | Abort button work |  |  |  |  | pass
| Edit Product Category | Verify when u edit product and add same product with the use of edit option , it should decline to be entered |  |  |  |  | pass
|  | Verify edit product |  |  |  |  | pass
|  | Verify abort and submit button work |  |  |  |  | pass
|  | Verify number not allows in category |  |  |  |  | pass
|  | Verify Title of edit popup |  |  | It should be "Edit Product Category" | Add Product Category | pass | https://cuneiform.atlassian.net/browse/ECPC-298 |  |  |  |  | Done 25.06.24
| Delete Category | Verify Inner delete button name | 1) Login 2) Click on Setting 3) Click on Product Catalogue 3) Click on Category 4) Select any one category 5) Click on delete button 6) Click on "Delete" |  | When we click on delete button then Popup comes, one "Delete" button is there. Delete button name should be "Yes" not "Delete" or "Yes Delete" |  | pass | https://cuneiform.atlassian.net/browse/ECPC-299 |  |  |  |  | No need to change
|  | Verify delete button work |  |  |  | Thinner deleted successfully | pass
|  | Check pegination |  |  |  |  | pass
|  | Verify cancel button work |  |  |  |  | pass
| Sub Categories | Verify Sub Category title Category Name/Actions |  |  | It should be as below : Subcategory Category Brand Actions Or Category Subcategory Actions | Here the titles are below : Category Name Actions | pass | https://cuneiform.atlassian.net/browse/ECPC-300 |  |  |  |  | Done 25.06.24
| Add Sub Categories | Verify Button name |  |  |  | Here it is "Add Sub Category" | pass
|  | Verify title of Add Sub Categories popup |  |  |  | "Add Sub Category" | pass
|  | Verify validation message |  |  | For Category - Please enter Category For Sub Category - "Please enter Sub Category" | For Category - Please enter category first For Sub category - "Please enter sub category first" | pass
|  | Verify in category field one drop box should be there |  |  | If drop box available then client can easily select category from the catelory list. Here they have to go back and write the category in category name. It is complex process. |  | pass
|  | Verify successfully add subcategory when we add category / Subcategory |  |  |  |  | pass
|  | Abort button work |  |  |  |  | pass
| Edit Sub Category | Verify when u edit Category, subcategory, duplicate entry should not allowed to be entered | 1) Login 2) Click on Setting 3) Click on Product Catalogue 3) Click on sub Categories 4) Select any one category 5) Click on edit button |  |  |  | pass
|  | Verify edit product |  |  |  |  | pass
|  | Verify abort and submit button work |  |  |  |  | pass
|  | Verify number not allows in category |  |  |  |  | pass
|  | Verify Title of edit popup |  |  |  | Update Sub Category | pass | https://cuneiform.atlassian.net/browse/ECPC-303 |  |  |  |  | Done 25.06.24
|  | When edit subcategory |  |  |  | I am trying to edit Sub Category name of below : 1) Category : Primer 2) Sub Category : Heat resistant I want to edit name as like below: Category:Primer1 Sub Category:Heat Resistant After edit and click on submit button one validation message comes like Subcategory details updated successfully. data is not saved but message comes like above. Please set the message "Category that you have entered is not available." or else. | pass | https://cuneiform.atlassian.net/browse/ECPC-304 |  |  |  |  | Done 25.06.24
| Delete Subcategory | Verify Inner delete button name | 1) Login 2) Click on Setting 3) Click on Product Catalogue 3) Click on Category 4) Select any one category 5) Click on delete button 6) Click on "Delete" |  | When we click on delete button then Popup comes, one "Delete" button is there. Delete button name should be "Yes" not "Delete" |  | pass | https://cuneiform.atlassian.net/browse/ECPC-302 |  |  |  |  | No Need of change
|  | Verify delete button work |  |  |  | Thinner deleted successfully | pass
|  | Check pegination |  |  |  |  | pass
|  | Verify cancel button work |  |  |  |  | pass
| Finish Type | Main title is "Finish", it should be "Finish Type" |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-306 |  |  |  |  | Done but different way Assign back 25.06.24 | Done 26.06.24
|  | Verify all title like Name/Actions |  |  | It should be as below Finish Type Actions |  | fail | https://cuneiform.atlassian.net/browse/ECPC-307 |  |  |  |  | Done but different way Assign back 26.06.24
| Add Finish Type | Verify add functionality | 1) Login 2) Click on Setting 3) Click on Product Catalogue 4) Click on Finish Type 5) Click on "Add Finish" 6) Enter field 7) Submit |  |  |  | Pass
|  | Verify validation message |  |  | It should be "Please enter Finish type" | In ERP validation message like "Please enter Finish name first" | fail | https://cuneiform.atlassian.net/browse/ECPC-305 |  |  |  |  | Not done Assign back 26.06.24
|  | Verify abort functionality |  |  |  |  | pass
|  | Verify dulpicate fishish type should not be allowed to be entered |  |  |  | Finish type already exists. | pass
| Edit Finish Type | Verify edit finish type title |  |  | It should be "Update Finish Type" | Add Finish | fail | https://cuneiform.atlassian.net/browse/ECPC-308 |  |  |  |  | Done but different way Assign back 25.06.24
|  | Verify when we edit any finish type, and edit/add duplicate finish type then it should not be allowed. |  |  |  | Finish type already exists. | pass
|  | Verify word limitation of Finish Type |  |  |  | Here set 30 character word limit | pass
| Delete Finish Type | Verify delete button functionality | 1) Login 2) Click on Setting 3) Click on Product Catalogue 4) Click on any Finish Type 5) Click on "Delete button" 6) Enter field 7) Submit |  |  | "Are you sure about deleteing Powder Polish Finish Type" you won't be able to revert this! | pass
|  | Verify cancel button functionality |  |  |  |  | pass
|  | Verify delete button functionality |  |  |  | "Powder Polishing deleted successfully" | pass
|  | Verify Pegination |  |  |  |  | pass
| UOM | Verify title UOM/Actions |  |  |  |  | pass
| Add UOM Functionality | Verify add UOM functionality |  |  |  |  | pass
|  | Verify the name |  |  |  | In ERP we have to mention the Full Name in field name of uom because unknown person can understand what they have to enter. Here, the name is "uom" please replace it with "Unit Of Mesurement" in the main title. In other place it is ok | pass | https://cuneiform.atlassian.net/browse/ECPC-309 |  |  |  |  | Done 26.06.24
|  | Verify validation message |  |  | It should be "Please enter UOM of paint" or “Please enter Paint UOM" Please don’t use first word | In ERP validation message like “Please enter Paint uom first”. | fail | https://cuneiform.atlassian.net/browse/ECPC-310 |  |  |  |  | Assign back 26.06.24
|  | Verify entering duplicate UOM |  |  |  | UOM already exists. | pass
|  | Verify first letter of the word should be capitalize when you enter |  | kilogram | First letter should be capitalize at the time of enter |  | pass | https://cuneiform.atlassian.net/browse/ECPC-311 |  |  |  |  | Done 25.06.24
|  | Verify abort button work |  |  |  |  | pass
|  | Verify when we entering UOM like second, minute , It should not be entered |  | Second Minute | Strict validation should be there not allowing to add second, minute etc It should be allowed only those UOM which are use in paint industries. Some UOM should be fixed for enter. | All UOM allowed to be entered. | fail | https://cuneiform.atlassian.net/browse/ECPC-312 |  |  |  | It is a input field user can enter any type of unit we can not add validation for every word | We have to ask to client which measurement maximum use in their industry then we can add it accordingly.
| Edit UOM Functionality | Verify title |  |  | It should be "Edit UOM" | Add UOM | fail
|  | Verify character enter |  |  | After entering characters first letter automatically converted in capitalize. |  | fail | https://cuneiform.atlassian.net/browse/ECPC-313
|  | Verify abort functionality |  |  |  | UOM update successfully. | pass
| Delete UOM Functionality | Verify delete functionality | 1) Login 2) Click on Setting 3) Click on Product Catalogue 4) Click on UOM 5) Click on "Delete button" of any UOM 6) Click Yes, Delete |  |  | "Are you sure about deleteing gramm?" you won't be able to revert this. Gram deleted successfully. | pass
|  | Verify actions button |  |  | It should be in center |  | fail
|  | Verify pegination work |  |  |  |  | pass
| Color | Verify all title like "Preview/Color Name/Ral Code/Hex Code |  |  | It should be Color Name, Preview, Ral Code, Hex Code | Titles given wrong. Here in "Color Name" title given a "Preview". In "Preview" title given "Color Name". | pass
| Add color | Verify title in add color like Title given as Name/Ral Code/Hex Code/Other |  |  | Title should be Name RAL Code HEX Code Other | Title given as Name/Ral Code/Hex Code/Other | pass
|  | Verify characters of RAL Color code - It should be 7 Alphanumeric . |  |  | It should not allowed more than 7 digits | I have entered color - RAL Dasdasdasdasdddddddddddddd. And it is allowed. | fail | https://cuneiform.atlassian.net/browse/ECPC-321
| RAL | Verify RAL color code - Digit and character both should be allowed. |  |  | Ral code should be combination of digit and character it means alphanumeric should be allowed. | In ERP - digits not allowed to be entered | fail | https://cuneiform.atlassian.net/browse/ECPC-322
| HEX | Verify character limit of HEX code |  |  | Hex code should be 7 alphanumeric . | HEX code should be 7 alphanumeric. Digits and characters both are allowed to be entered. Here we are unable to enter anything. Name fetched here. it means by default, the Name field comes in HEX code field. i.e When we enter name "RED", RED comes in HEX field. Digits and text are not allowed to be entered. | fail | https://cuneiform.atlassian.net/browse/ECPC-323
|  | Verify validation message |  |  | It should be as below: please enter color name Please enter RAL Code Please enter HEX Code Please provide details in the 'Other' . | Name : please enter color name first RAL: Please enter Ral Code First HEX: Please enter Hex Code first Other: Please difine some characteristics of the Paint | fail | https://cuneiform.atlassian.net/browse/ECPC-324
|  | Verify submit button functionality |  |  |  | Not work | fail | https://cuneiform.atlassian.net/browse/ECPC-325
|  | Verify seach button |  |  | Seach button should be there. If clients want to search, some color is available or not in the list then they will find by search option. | Here seach button is not available. | fail | https://cuneiform.atlassian.net/browse/ECPC-326
Phase -II Testing
08.08.24 | Brand | Add Brand successfully |  |  |  |  | pass
|  | Edit brand sucessfully |  |  |  |  | pass
|  | Brand deleted successfully |  |  |  |  | pass
|  | When we deleted any brand , It should not be displayed in the category list. Here, I have deleted brand "Testbrand2"in the brand but I can see "Testbrand2" along with category Name "Tinters" |  |  |  |  | pass | [5 empty] | 14.08.24 Now it is resolved
|  | Verify pagination |  |  |  |  | pass
Categories
|  | "Margin Percentage" column should be came in table of Product category beside the "Brand Name" column |  |  |  |  | pass | [5 empty] | 14.08.24 Now it is resolved
| Add Product category | Validation message for margin%-It should be Please enter margin percentage Here it is "Please enter Brand Id" |  |  |  |  | pass | [5 empty] | 14.08.24 Now it is resolved
|  | In category name -All special characters should not be allowed. Here it is allowed |  |  |  |  | pass |  | 9.1 |  |  | Done but not deployed | Client has already provided the list of category. There is no any special characters are used in category name. We can allow "." and "-" but other special characters should not be allowed | Done 05.09.24
| Product Category-Update | When we click on edit button of any product - Zero comes by default in Margin percentage. Please remove it. Because when user click on and add margin then 0 takes by default then value of margin has been changed I have enter 10 then it displays 01. |  |  |  |  | pass |  | 9.2 |  |  | if client requests then we will change this, according to me it is fine Done but not deployed | From my point of view, we should provide a blank field. The '0' margin is currently set by default, but when the user clicks on it, they should be able to add a margin directly without needing to remove the '0' first. If possible, please implement this change. | Done 05.09.24
|  | In Category name-It should be disable because we have already provided edit button in particular field Need to discuss |  |  |  |  | pass | [5 empty] | 14.08.24 Now it is resolved
| Delete | Product Categories deleted successfully |  |  |  |  | pass
SubCategories
| Add Sub Category | Verify Subcategory added successfully |  |  |  |  | pass
|  | Digits and special characters should not be allowed in Subcategory Name |  |  |  |  | fail |  | 9.3 |  |  | We have allowed digits or special character . For example if he wants to enter category thinner2.O then he can add it as per is call | "." and "-" should be allowed but other special characters should not be allowed like *,&,^,%,$,#,@
| Edit Sub Category | Edit subcategory successfully |  |  |  |  | pass
| Delete Sub category | Delete record successfully |  |  |  |  | pass
SubChild Categories
|  | Validation message - Subchild category - It should be "Please enter sub child category" Here, it is "Please enter sub category" |  |  |  |  | pass |  | 9.4 |  |  | Done | Done 30.08.24
| Add Subchild Category | Verify Sub child category added successfully |  |  |  |  | pass
|  | Digit along with subcategory name should be allowed to be entered But Special characters should not be allowed in Subchildcategory Name. Here, it is allowed to be entered |  |  |  |  | pass |  | 9.5 |  |  | We have allowed digits or special character . For example if he wants to enter category thinner2.O then he can add it as per is call Done but not deployed | "." and "-" should be allowed but other special characters should not be allowed like *,&,^,%,$,#,@ | Done 05.09.24
| Edit Sub Category | Verify Edit subcategory successfully |  |  |  |  | pass
| Delete Sub category | Verify subchild category record successfully |  |  |  |  | pass
Paint type
| Add Paint type | Please update validation message "Please enter Paint name" It should be "Please enter Paint type name" |  |  |  |  | pass |  | 9.6 |  |  | Done | Done 30.08.24
|  | Digit should be allowed along with name of Paint type it is ok But Special characters are not allowed Here It is allowed to be entered Pls update in Update Paint type too |  |  |  |  | fail |  | 9.7 |  |  | It will get changed only if client says , as we do not have provide the docs for validation | We already know that, In Paint type special characters are not allowed . Example Matte@, Oilbased #, Cement Paint % Not possible . "." and "-" should be | Not Done 05.09.24
| Edit Paint type | Verify validation msg in Update Paint type Please update message - "Please enter Paint name" It should be "Please enter Paint type name" Also update same in place holder |  |  |  |  | pass |  | 9.8 |  |  | Done | Done 30.08.24
| Delete Paint type | Verify Product deleted successfully |  |  |  |  | Pass
Finish type
| Add Finish Type | Verify add finish type successfully |  |  |  |  | Pass
|  | Digit along with Finish type should be allowed But All Special characters should not be allowed in Add finish type Pls Update in Update Finish type too |  |  |  |  | Fail |  |  |  |  | Done | Not Done 30.08.24 | "Not Done 05.09.24"
|  | Please update validation message "Please enter Finish name" It should be "Please enter Finish type name" |  |  |  |  | pass |  | 9.9 |  |  | Done | Done 30.08.24
| Edit Finish Type | Verify Edit finish type successfully |  |  |  |  | Pass
| Delete Finish Type | Verify Delete Finish type successfully |  |  |  |  | Pass
Color
| Add Color | Verify In color Name - All special characters should not be allowed. Here it is allowed name like : Red (13,16,89,12) RED% Orange$ |  |  |  |  | pass |  | 10 |  |  | client has't provided us any information for the color code so we can't add any validations right now | Yes , client has not provided color names but when we given facility to entering special characters along with color code then it is ok But in color name special character not allowed. "." and "-" should be allowed only. | Talked with developer they had discussed with client
| Edit | Action button-Edit button not available. It should be there. |  |  |  |  | pass |  | 10.1 |  |  | client has't provided us any information for the color code so we can't add any actions on the table Done but not deployed | For action button we don't have permission or informtaion from the client. When we enter wrong color name/code than how can we edit it. also we don't have the delete button | Done 05.09.24
| Delete | Action button - Delete button not available It should be there. |  |  |  |  | pass |  | 10.1 |  |  | Done but not deployed | From my point of view , delete button should be there so that spam data will not be added | Done 05.09.24

## Inventory
DATE OF CREATION | 04.07.24 |  |  |  |  | TOTAL PASS
MODULE NAME | Inventory |  |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 0
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
13.08.24 | Title | Verify title like SKU/Products Name/Stock Quantity/Minimum Stock Quantity/Sold/Create On |  |  | It should be SKU/Products Name/Stock Quantity/Minimum Stock Quantity/Sold/Create On | Here it is SKU/Products Name/Stock Quantity/MInimum Stock Quantity/Sold/Create On | Pass | [5 empty] | Done 25.06.24
|  | Column should be Products Name/SKU/Stock Quantity/Minimum Stock Quantity/Sold/Create On |  |  | In Inventory - product name comes in First column when user want to search any product by product name then they are not confused. For uniformity and user friendliness approach, we have take two same column in same place |  | pass | [5 empty] | Coloumn removed. Done 25.06.24
| Filter | Filter button functionality |  |  |  |  | Pass
| Search | Search button functionality |  |  |  |  | Pass
| View Inventory | Verify details like Products Name/Stock Quantity/MInimum Stock Quantity/Sold/Create on |  |  | Verify details like Product Names/Stock Quantity/Minimum Stock Quantity/Sold/Created on |  | fail | https://cuneiform.atlassian.net/browse/ECPC-342
| Invetory Details | Path should be Inventory/Inventory Details. Here it is "Dashboard/Invetory/Inventory Details. |  |  |  |  | fail | https://cuneiform.atlassian.net/browse/ECPC-343
| Basic details | Verify details like SKU Number/Product Name/Brand/Category/Color/PackSize UOM |  |  | Here , Products Name/SKU Number/ Brand/ Category/ Color/ Pack Size UOM |  | pass | https://cuneiform.atlassian.net/browse/ECPC-344 |  |  |  |  | No need to do developer don’t want to change
| Update Inventory | "Update Inventory" main title |  |  |  |  | pass
|  | Verify title like Warehouse Name/Quantity/Minimum Quantity/Action |  |  |  |  | pass
| Update Inventory form | Update inventory titles like Quantity/Minimum Quantity/Add products |  |  | It should be Quantity/Minimum Quantity/Add Products Quantity | Here it is given "Add Products" title . User can be confused with this title and add the product name. | pass | https://cuneiform.atlassian.net/browse/ECPC-345 |  |  |  |  | 13.08.24 Form has been changed
|  | Quantity comes in green color |  |  | When quantity reach with their limit then font should be in different color like red |  | pass | https://cuneiform.atlassian.net/browse/ECPC-346 |  |  |  |  | 13.08.24 Changed font color with red when min quantity alert comes
|  | Verify button functionality of remove |  |  |  |  | pass
|  | Verify submit button functionality |  |  |  |  | pass
| Abort | Verify Abort button functionality |  |  |  |  | pass
| Other Details | Verify Title Paint Type/FinishType/Sub Category/Sub Child Category/Description |  |  |  |  | pass | [5 empty] | Done 25.06.24
| Paint Formulla | Verify title like Base Paint 1/Proportion Of Paint 1/UOM/Tinters 1/Proportion of Tinters/UOM/Base Paint 2/Proportion of Paint 2/UOM/Total Quantity Produce |  |  | It should be as below : Base Paint 1 Proportion Of Paint 1 UOM Tinter 1 Proportion Of Tinter UOM Base Paint 2 Proportion Of Paint 2 UOM Total Quantity Produce |  | pass | https://cuneiform.atlassian.net/browse/ECPC-347 |  |  |  |  | 13.08.24 Form has been changed
| Price details | Verify title like Price Detail |  |  | It should be "Price Details" |  | fail | https://cuneiform.atlassian.net/browse/ECPC-348
|  | Verify title like Unit Price/Cost Price/Selling Price |  |  |  |  | Pass
|  | Counting of unit price/cost price/selling price seems wrong, logic seems wrong need to talk |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-349 |  |  |  |  | 13.08.24 Done
|  | One button should be there for the selection of number of pages like 15/25/30 pages etc. |  |  |  |  | fail | https://cuneiform.atlassian.net/browse/ECPC-350
Phase -II Testing
13.08.24 | Title | Verify title like SKU/Products Name/Stock Quantity/Minimum Stock Quantity/Sold/Create On |  |  | It should be SKU/Products Name/Stock Quantity/Minimum Stock Quantity/Sold/Create On | Here it is SKU/Products Name/Stock Quantity/MInimum Stock Quantity/Sold/Create On | Pass | [5 empty] | Done 25.06.24
|  | Column should be Products Name/SKU/Stock Quantity/Minimum Stock Quantity/Sold/Create On |  |  | In Inventory - product name comes in First column when user want to search any product by product name then they are not confused. For uniformity and user friendliness approach, we have take two same column in same place |  | pass | [5 empty] | Column removed. Done 25.06.24
| Path on top | Inventory path should be "Inventory" inplace of "Dashboard/Inventory |  |  |  |  | fail | https://cuneiform.atlassian.net/browse/ECPC-341
| Filter | Filter button functionality |  |  |  |  | Pass
| Search | Search button functionality |  |  |  |  | Pass
| View Inventory | Verify details like Products Name/Stock Quantity/MInimum Stock Quantity/Sold/Create on |  |  | Verify details like Product Names/Stock Quantity/Minimum Stock Quantity/Sold/Created on |  | Pass | [5 empty] | No need to do
| Basic details | Verify details like SKU Number/Product Name/Brand/Category/Color/PackSize/UOM |  |  | Here , Products Name/SKU Number/ Brand/ Category/ Color/ Pack Size/ UOM |  | pass | [5 empty] | No need to do developer don’t want to change
| Update Inventory | "Update Inventory" main title |  |  |  |  | pass
|  | Verify title like Warehouse Name/Quantity/Minimum Quantity/Action |  |  |  |  | pass
| Update Inventory form | Update inventory titles like Quantity/Minimum Quantity/Add products |  |  | It should be Quantity/Minimum Quantity/Add Products Quantity | Here it is given "Add Products" title . User can be confused with this title and add the product name. | pass | [5 empty] | 13.08.24
Form has been changed
|  | Quantity comes in green color |  |  | When quantity reach with their limit then font should be in different color like red |  | pass | [5 empty] | 13.08.24
Changed font color with red when min quantity alert comes
|  | Verify button functionality of remove |  |  |  |  | pass
|  | Verify submit button functionality |  |  |  |  | pass
| Abort | Verify Abort button functionality |  |  |  |  | pass
| Other Details | Verify Title Paint Type/FinishType/Sub Category/Sub Child Category/Description |  |  |  |  | pass | [5 empty] | Done 25.06.24
| Paint Formulla | Verify title like Base Paint 1/Proportion Of Paint 1/UOM/Tinters 1/Proportion of Tinters/UOM/Base Paint 2/Proportion of Paint 2/UOM/Total Quantity Produce |  |  | It should be as below : Base Paint 1 Proportion Of Paint 1 UOM Tinter 1 Proportion Of Tinter UOM Base Paint 2 Proportion Of Paint 2 UOM Total Quantity Produce |  | pass | [5 empty] | 13.08.24 Form has been changed
| Price details | Verify title like Price Detail. It should be "Price Details" |  |  |  |  | pass |  |  |  |  | Done | Done 30.08.24
|  | Verify title like Unit Price/Cost Price/Selling Price |  |  |  |  | Pass
|  | Counting of unit price/cost price/selling price seems wrong, logic seems wrong need to talk |  |  |  |  | pass | [5 empty] | 13.08.24 Done
13.08.24 | Update Inventory | "Remove inventory button" should be there and this option is accessible by Admin/Super Admin only. I have updated/added inventory by mistake and want to remove it but here there is no option for remove inventory. Here created wrong updation of inventory stock. |  |  |  |  | fail | [5 empty] | Not done 30.08.24
|  | Please check the counting sometimes it is wrong. When we update inventory |  |  |  |  | Pass
02.09.24 | Update Inventory functionality | Verify functionality when we add any new product and update quantity in inventory |  |  |  |  | Pass
|  | Verify Functionality when we "Create New Product" and update quantity in inventory |  |  |  |  | Pass
|  | When we update inventory in the create new product , Automatically quantity minus from the base 1 /Base 2/Tinter product |  |  |  |  | Pass
|  | There is no option when we are selling of Base 1/Base 2 . It means when we are selling Base 1 Product then Inventory of Base 1 product quality should be minus. Here there is no any option for this. only "add quantity" functionality works in update inventory but when we selling any product at that time it should subtract from the current quantity. Here only focused on "New Create Product" quantity update |  |  |  |  | Fail |  |  |  |  | Done but not deployed

## Stock Management
DATE OF CREATION | 04.07.24 |  |  |  | TOTAL PASS
MODULE NAME | Stock Management |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS |  |  |  |  | TOTAL TEST CASES | 0
Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
Stock Management | Title-Stock Management path seems to be wrong |  |  |  | Dashboard/Stock Movements | Pass
Stock Movement | Verify title of stock movements like Transaction Id/From Store/To Location/Numbers of items/Created On/Created By |  |  |  |  | Pass
2.6

## Product Mananagement
DATE OF CREATION | 13.06.24 |  |  |  |  | TOTAL PASS
MODULE NAME | Product Management |  |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 0
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
| Header | Verify Profile Pic button functionality |  |  |  |  | pass
|  | Verify Notification button functionality |  |  |  |  | remaining
|  | Paths seems wrong |  |  | Product is not a category of dashboard, dashboard is also an option by self. Dashboard and Product priority are same. No need to give path or Please refer Figma . It should be Products | Dashboard/Products | fail | https://cuneiform.atlassian.net/browse/ECPC-270 |  |  |  |  | Need to change but Needs to discuss with dev
| Product List Header | Verify Search button |  | Futura |  |  | pass
|  | Verify filter button functionality |  |  |  |  | pass
|  | Verify reset all button functionality |  |  |  |  | pass
|  | Verify all button height should be same for Search /Filter/Add New Product/Create New Product" |  |  |  | Button height seems different | fail | https://cuneiform.atlassian.net/browse/ECPC-271 |  |  |  |  | Assign Back 26.06.24
|  | Verify button name of Create and Add New Product |  |  | It should be 1) Add Product 2) Create New Product | Here it is 1) +Create 2) Add New Product | pass | https://cuneiform.atlassian.net/browse/ECPC-273 |  |  |  |  | Done 26.06.24
|  | Verify place of button of Create/Add New Product |  |  | Order should be 1) Add Product 2) Create New Product | Here it is 1) +Create 2) Add New Product | pass | https://cuneiform.atlassian.net/browse/ECPC-277 |  |  |  |  | Done 26.06.24
| Product list title | Verify title SKU/Product Name/Description/Brand/Category/Created By/Created on |  |  | It should be as below : Product Name SKU Description Brand Category Created By Created On Because SKU fetched by the product name. | In ERP "SKU" number is blank. When we enter product name, SKU filled | pass | [5 empty] | Done 02.07.24
| Add New Product | Verify Title of Popup |  |  | It should be "Add Product" | "Add A New Product" | pass | https://cuneiform.atlassian.net/browse/ECPC-278 |  |  |  |  | Done 26.06.24
|  | Verify title like product Name/Description/Brand/Category/Sub Category/Sub Child Category/Color/Pack Size/UOM/Paint Type/Finish Type/HSN..SAC Code/Unit Price/Cost Price/Selling Price |  |  | I think description field is not required |  | pass | https://cuneiform.atlassian.net/browse/ECPC-279 |  |  |  |  | Freya will discuss with client 26.06.24 talked with devloper no need to do
|  | Dropbox should be required in the field of Brand/Category/Sub Category/Sub Child Category/Paint type/Finish type etc |  |  | Here dropbox is required because users have to enter all the necessary details here. Everytime they are not remembering. If they forget any details. They have to go back and check all data list. This is tedious work for the user. And also wasting time for that. | Drop box not available | pass | https://cuneiform.atlassian.net/browse/ECPC-280 |  |  |  |  | Done 26.06.24
| "+Create" - New Paint Formula | Verify all title like Paint Name/Brand/Category/Sub Category/Sub Child Category/Pack Size/UOM/Base Paint 1/Proportion of Paint 1/UOM/Tinter1/Proportion of Tinters/UOM/Base Paint 1/Proportion of Paint 2/UOM/Color/HSN Code/Total Quantity Produce/Paint Type/Finish Type/Unit Price/Cost Price/Selling Price |  |  |  |  | Pass
|  | Verify Brand, Category, Sub Category, Sub Child Category should be comes in drop box so that user can select from the drop box. |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-281 |  |  |  |  | Done 26.06.24
|  | Verify Brand - Digit and special characters should not be allowed. If we are not set drop box . |  |  |  |  | Pass | No need
|  | Pack size-No need of pack size here |  |  |  |  | pass | No need
|  | First letter of the word of Paint Name / Base Paint 1 and 2 should be capitalized automatically when entering their name |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-282 |  |  |  |  | Done 26.06.24
|  | We can also add all list of Base Paint 1, Base Paint 2, Tinter 1 and other, so user can select name from the drop box- It is not possible to remembering all name . |  |  |  | Here user has to enter the name for all. so they can not remember all name. | pass | https://cuneiform.atlassian.net/browse/ECPC-283 |  |  |  |  | Done 26.06.24
|  | Verify character should not be allowed in Proportion of Paint 1 |  |  |  |  | Pass
|  | Verify - Propotion of Paint 1 and 2 - Eight to Nine digits or ten digit should be allowed max Ex.000000000 |  |  |  | Here it is allowed 81 digits | pass | https://cuneiform.atlassian.net/browse/ECPC-284 |  |  |  |  | Done 26.06.24
|  | Verify - In tinter 1 and other - Eight to Nine digits should be allowed max Ex.000000000 |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-285 |  |  |  |  | Done 26.06.24
|  | Verify any UOM should be selected compulsory |  |  |  | Here without selecting UOM, it is allowed to add. Not any validation message comes | pass | Messages comes
|  | Verify HSN number maximum limit of digits |  |  | It should be 6 to 8 digits max. So, we have to set 8 digits max and Minimum six digits should be allowed. | Here it is allowed 81 characters. And after filling the full form, validation message comes. Strict validation for not allowing to enter more than 8 digits max and 6 digits min. | pass | https://cuneiform.atlassian.net/browse/ECPC-286 |  |  |  |  | Done 26.06.24
|  | Verify charcters are not allowed in HSN number, Only digits should be allowed to be entered. |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-288 |  |  |  |  | Done 26.06.24
|  | Verify I can not understand logic of color |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-289 |  |  |  |  | Done 26.06.24
|  | Verify "Total Quantity Produce" |  |  | It should be fetched from the list of Proportion of paint 1,2 and tinter 1 and other tinter. |  | pass | https://cuneiform.atlassian.net/browse/ECPC-290 |  |  |  |  | Assigned in Jira to Dev.prateek | Done 02.07.24
|  | Verify "Total Quantity Produce" digit limit |  |  | It should be max 20 digits or as per ur understanding. Ex.000000000000000.. Also consider when we add Porportion of paint 1/2 , Tinter 1….other etc. | Here it is allow 81 characters Ex. 444444444444444444443333333333333333333333333333333333333333333333333333777777777 | pass | https://cuneiform.atlassian.net/browse/ECPC-291 |  |  |  |  | We have to think We have to think about this because it will be the total of the proportion paint1/ paint 2/Tinter1 and other. Paint 1 - 100000ml Paint 2 - 100000ml Tinter1 - 5000ml Tinter2 - 5000ml Then the total quantity should be 2,10,000 ml. Here, we have set the limit of five digits. So 2,10,000ml will not be fetched in the future. Assign back 26.06.24 | Done
|  | Verify text should not be allowed in "Total Quantity Produce" |  |  |  |  | Pass
|  | Verify space is not allowed in the "Total Quantity Produce" |  |  |  | Here 868 78767 7678687 76876876 6876876 8766786876876876 allowed | pass | https://cuneiform.atlassian.net/browse/ECPC-292 |  |  |  |  | Done 26.06.24
|  | Create New Paint--Verify Paint type and Finish type - drop box is required here |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-293 |  |  |  |  | Not done 26.06.24 | Done 02.07.24
|  | Verify add tinter functionality |  |  |  |  | pass
|  | Verify remove tinter functionality |  |  |  |  | pass
|  | After adding HSN number wth 8 digits, message comes like HSN Code is required |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-327 |  |  |  |  | Assign in Jira 26.06.24 | Done 02.07.24
|  | Create New Paint - If we select ml in proportion 1, then in proportion of 2, tinter1 and other will come in ml. Here, it is given the option for selecting anything like kg, ml, test etc |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-328 |  |  |  |  | Assign in Jira 26.06.24 | Done 02.07.24
| Edit product price | When we add any product and update their Unit price then cost price should be changed accordingly Example : Here I have update price of below : Quantity : 5 Unit price 100 Cost Price: 500 Selling Price: 2000 Now I updated Unit price Rs 150. Then I get output like : Quantity : 5 Unit price 150 Cost Price: 300 Selling Price: 200 |  |  | It should be as below: Quantity : 5 Unit price 150 Cost Price: (5X150=750) Selling Price: 200 one message should be came like "Selling price is not less than of cost price" when selling price less than cost price. Also in cost price should be came like Quantity X Unit price. |  | pass | https://cuneiform.atlassian.net/browse/ECPC-335 |  |  |  |  | Assign in Jira 26.06.24 | Done 02.07.24
|  | Verify all validation message |  |  | Please update as below: "Selling Price is required" | "Unit Price is required" Cost Price is required" "selling Price is required" | pass | https://cuneiform.atlassian.net/browse/ECPC-336 |  |  |  |  | Assign in Jira 26.06.24 | Done 02.07.24
| Comment | Verify comment added successfully |  |  |  | Comment added successfully | pass
| Product Details | Path seems to be wrong. It should be Products/Product Details |  |  |  | Here it is Dashboard/Products/Products Details | fail | https://cuneiform.atlassian.net/browse/ECPC-337 |  |  |  |  | Assign in Jira 26.06.24
| Add Product | Description text should not come in the first letter of the word in capital. It should be only the first letter capital. |  |  |  |  | fail | https://cuneiform.atlassian.net/browse/ECPC-338 |  |  |  |  | Assign in Jira 26.06.24
|  | One button should be there for the selection of number of pages like 15/25/30 pages etc. |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-339 |  |  |  |  | Assign in Jira 26.06.24 | Keep this in CR
|  | If we select Base 1 paint in ml Tinter in box paint 2 in kg then how it will count Here no any calculation seems |  |  |  |  | pass | https://cuneiform.atlassian.net/browse/ECPC-340 |  |  |  |  | Assign in Jira 26.06.24 | Done 02.07.24
Phase -II Testing
12.08.24 | Search | Verify Search button functionality |  |  |  |  | pass
| Filter | Verify Filter button functionality |  |  |  |  | pass
| Add Product | Verify Title - "Selling Price", it should be "Selling Unit Price" . So that user can understand this is the price for a single unit |  |  |  |  | pass |  |  |  |  | Done | "Done 30.08.24"
|  | Verify add product functionality |  |  |  |  | pass
| Edit Product | Verify Edit - Basic details successfully |  |  |  |  | pass
| Create New Product | Verify create product successfully | 1) Logged In with credential 2) Click on Product Name 3) Click on Add Product button 4) Fill details like ProductName/Product Type/Product Standarad/Product Code/HSN..Sac code/Product Description/Brand/Category/SubCategory/SubChileCategory/Pack size/Pack Quanity/Color/Paint Type/Finish Type/Unit Price/Cost Price | Testingproduct 1212 Non Standard Product Jotun Tinters Red 32159090 6 5.9 Oil Based Matt 10 100 |  |  | pass |  |  |  |  | Done | "Done 30.08.24"
|  | Product Code should be generated automatically. Here, I have entered the same product number in two different product names but it should not be allowed to be entered |  | 12123 |  |  | pass | [5 empty] | No needs to do talked with dev, client wants it
|  | Base Paint 1 and Base paint 2, both products name are different from eachother when we are creating new product. Here it is added with the same product name. Same product adding doesn’t mean, It will create same product. Some validation should be there |  |  |  |  | pass |  |  | Done |  | Done | "Done 30.08.24"
|  | When we create product with Base 1/Tinter/Base 2 same name with same content of protion. it is not allowed to be enter and one validation message comes like : "This product exist with name "Test Test". Here Validation message should be came like "This product exist with name "Test create new". It means it display a "existing product name". not a new create paint name. discussed with dev kinjal leuva |  |  |  |  | pass |  | 5.1 |  |  | Done but not deployed | New 30.08.24
|  | Verify Duplicate product should not be allowed. Here, I have created a product with same name with same field and allowed to be entered but it should not be allowed. Also created the same SKU : JO-TO-F2296-TE/12.00 | 1) Logged In with credential 2) Click on Product Name 3) Click on Create New Paint 4) Fill below details PaintName Product Standarad Product Code HSN Number Brand Category SubCategory Base Paint1 Proportion Paint 1 Tinter1 Proportion of tinter Base Paint2 Proportion Paint 2 Color Paint Type Finish Type | Testcreate Standard Product 0101 32159090 Jotun TopCoat Red Test 121 1 Tinter1 1 Test 122 1 Red Oil Based Matt |  |  | pass |  | 5.1 |  |  | Done | Done 30.08.24
|  | One button should be there for the selection of number of pages like 15/25/30 pages etc. So, user can navigate easily. If a user is on page no 275 then how can they navigate on 50 page. They have to click one by one page and reachout on 50 page no |  |  |  |  | fail |  |  | Will be done on client requirement |  | Will be done on client requirement | It will be put in CR
|  | When we are trying to edit the product with the "Product name" which was not created, then it is saved. However the name is not displayed. Example : I have edit the product items which is used in "test new create" product like tinter with name tinter 7 which is not created here it is saved. It should not be saved. However the item "tinter - 7 " is not displayed when we click on the product view. |  |  |  |  | fail |  | 5.2 |  |  | Done but not deployed | When editing any details of product which is not available (means not created), the message is coming like "Product details updated successfully" But strict validation should be there not allowing to display message However it is not allowing to save it. Ex. If white color is not available and I am trying to edit it with white color which is not existed. then after save it display message like "Product detaiils updated successfully."
|  | Please update the text of "Produce Quantity In liters" with "Produce Quantity In Litres" Also change the spelling of "Liter" with "Litres" when we enters Quantity |  |  |  |  | fail |  | 5.3 |  |  | Done but not deployed | Not Done 05.09.24
|  | When we update/Edit any items in product details at that time one validation message comes and not allowing to edit any product details, Discussed with Dev. Kinjal Leuva |  |  |  |  | pass |  | 5.4 |  |  | Done but not deployed | Done 05.09.24
| Product Details | Color Name - special character - Only allows "#" "-" "." and characters and digits Other special characters should not be allowed |  |  |  |  | pass |  | 5.5 |  |  | client has't provided us any information for the color code so we can't add any validations right now | "Not Done 30.08.24" | Talked with Developer No need to change they have talked with client
| Edit Product Details | When we are trying to edit product name with same product name which is already exist then it is allowed here. It should not be allowed Ex.Test 04 - I have edited this name with Test 09 which is already Existed. Here it is allowed to be edited but it should not be allowed |  |  |  |  | fail |  | 5.6
| Footer | Pls update a text "About Us", "Contact Us" in the footer of main page |  |  |  |  | pass |  | 5.7 |  |  |  | Done 18.09.24
| Button | Verify all button height should be same for Search /Filter/Add New Product/Create New Product |  |  |  |  | fail | [5 empty] | Discussed with dev. Urvi
| Add Product | Description text should not come in the first letter of the word in capital. It should be only the first letter capital. |  |  |  |  | fail

## Sales
DATE OF CREATION | 03.09.24 |  |  |  |  | TOTAL PASS
MODULE NAME | Sales |  |  |  |  | TOTAL FAIL
REDIRECT ON SCENARIOS | [5 empty] | TOTAL TEST CASES | 0
Date | Sub-Module | Test Case Description | Test Steps | Input Data | Expected Result | Result | Status | JIRA Ticket ID# | Screenshot | Designer Bug | Designer Comment | Developer Comment | QA Comment | Round 1 Date/Comment | Round2 Date/Comment
03.09.24 | Sales Quatation Main | Verify Search button functionality
Verify Filter of "Creation status" i.e All/Draft/Sent
Verify deal status filter All/Accepted/Rejected
|  | Verify UI - Search button/Creation Status/Deal Status/Create Sales Quotation in the same aligned |  |  | All should be in same aligned | Here, it is not in same aligned | fail |  | 11.1
|  | Verify title of sales quatation |  |  | It should be SQ Number/ Company Name/ Deal Status/ Total Amount/ Creation Status/ Creation Date/ Created By | It comes like below: SQ Number/ Company name/ Deal Status/ Total Amount/ Creation Status/ Creation date/ Created By | fail
Create Quaotation-Sales Quatation Inner
| Edit Buyers Details | Verify Edit details of the Buyers
| Edit Delivery Location | Verify functionality of the edit delivery location details
| Supplier Details | Verify Supplier details fetch correctly
| Edit Primary Document Details | Verify Edit the primary document details successfully
| Search Products | Verify Search button functionality
| Verify details of products | Verify Details like SKU/Product Name/Product Code/HSN Code/Pack Size/Pack Quantity/No f Packs/Total Quantity/Previous Unit Price/Unit Price/Margin/Final Unit Price/Amount/Tax/Total Amount/Delivery Date/Additional details |  |  | It should be as below : SKU Product Name Product Code HSN Code Pack Size Pack Quantity No. Of Packs Total Quantity Previous Unit Price Unit Price Margin Final Unit Price Amount Tax Total Amount Delivery Date Additional Details Please update the text as above. | It comes like below : SKU Product Name Product Code HSN Code Pack Size Pack Quantity No. of packs Total Quantity Previous Unit Price Unit Price Margin Final Unit Price Amount Tax Total Amount Delivery Date Additional Details | fail
Verify the validation message "Please fill data first!"
| Add Product Details | Verify Functionality of add products
| Delete Products | Verify Delete button functionality
| Extra charges | Verify spelling of Extra Charges / Comments / Attach Signature/Terms and Conditions |  |  | It should be as below: Extra Charges Comments Attach Signature Terms and Conditions Please update text as above | It comes as below: Extra Charges Comments Attach Signature Terms and Condition | fail
| Add ExtraCharges | Add Extra charges button functionality
Delete button functionality
| Attach Signature | Verify upload signature successfully
| Format Terms and Conditions | Verify format Terms and Conditions text
Verify the submit button functionality
|  | Verify text like Subtotal/Taxes/Grand Total/Advance to pay |  |  | It should be as below : Subtotal Taxes Grand Total Advance To Pay Please update as above | Subtotal Taxes Grand Total Advance to pay | fail
Verify Characters and special characters should not be allowed in "Advance To Pay"
| Button | Verify cancel button functionality
Verify save draft button functionality
Verify preview button functionality
| Preview Functionality | In PAN number title comes "GST Number". It should be "PAN"
Verify Buyers and Suppliers details
Contact number should be in 10 digits
Characters and special characters are not allowed in contact number
Verify format of Buyers and Suppliers details
Verify Delivery location address details
Verify Delivery location - contact number - It should be ten digits and special character and characters are not allowed
| Sales Quatation details | Verify all details fetched correctly in sale quotation details
Verify Quotation details title like Product Name/HSN Code/Pack Quantity/No. of Packs/Total Quantity/Total Amount
Verify date format
Verify character and special characters are not allowed in date field
Verify number of items should be in digits
Verify transportation cost should be in digit
Verify GST number should be 15 digits
| Delete | Delete sale quotation button functionality
| Download | Download sale Quatation functionality
| Edit | Verify Edit button functionality
| Save and Send | Verify Save and Send button functionality
Please change the speling of "Terms and condition" It should be "Terms and Conditions"
Sales Details
| Sales Order | Verify Order Number/SO Number/Company/Delivery Date/Delivery Status/Creation Status/Creation Date/Total Amount/Created By
Verify date format should be DD/MM/YYYY or MM/DD/YYYY charcaters and special characters are not allow
| Sales Return | Verify title like Sales Return No./Sales Proforma Invoice No./Company Name/Creation Date/Delivery Date/Created By/No. Of Items/Sales return QTY |  |  | It should be as below : Sales Return No. Sales Proforma Invoice No. Company Name Creation Date Delivery Date Created By No. Of Items Sales Return Qty. Pls change as per above. | It comes like below : Sales Return No. Sales Proforma Invoice No. Company name Creation Date Delivery Date Created By No. of Items Sales Return Qty | fail
Verify Total amount should be comes in digits only. Characters and special characters should not be allowed
| Sales Proforma Invoice | Verify title like Invoice Number/Company/Title/Delivery Date/Creation Status/Creation Date/Total Amount/Created By |  |  | It should be as below: Invoice Number Company Title Delivery Date Creation Status Creation Date Total Amount Created By | It comes like below: Invoice Number Company Title Delivery Date Creation Status Creation Date Total Amount Created By
Verify Delivery date format Text and special characters should not be allowed
Verify total Amount - only digits should be allowed
| Delievry Challan | Verify title like Challan No./Sales Order No./Company Name/Creation Date/Delivery Date/No.Of Items/Total Amount |  |  | It should be as below: Challan No. Sales Order No. Company Name Creation Date Delivery Date No.Of Items Total Amount | It should be as below: Challan No. Sales Order No. Comapany name Creation Date Delivery Date No.of Items Total Amount
Verify the date format of creation date - Characters and Special characters are not allowed
Verify the date format of Delivery date - Characters and Special characters are not allowed
Verify No of item should be in digits only. Characters and Special characters should not be allowed
Verify Total Amount-It should be in digit only. Characters and Special characters should not be allowed
| Sales Person | Verify title like Sales Person/Brand/Month/Year/Total Sales Order/Total Amount
Verify year should be in 4 digits Ex. 2004
Verify month should be in characters Ex. January
Verify Total Sales order-Only Digits should be allowed
Verify Total Amount-It should be in digits only-Special characters and characters should not be allowed
Create Sales Quatation
Add Functionality
Edit button Functionality
Add product Functionality
Sales Details

## Bug Summary Report
TEST RESULT SUMMARY REPORT
Sr. No. | Module Name | Total Passed | Total Failed | Total Cases
1 | Sign Up Page(Registration) | 0 | 0 | 0
2 | Sign Up Page | 0 | 0 | 0
3 | Login Page | 0 | 0 | 0
4 | Dashboard | 0 | 0 | 0
5 | Profile | 9 | 22 | 31
6 | Buyer And Suppplier Management | 76 | 38 | 114
7 | User Management | 15 | 38 | 53
8 | Product Management | 0 | 0 | 0
9 | Profile Management | 0 | 0 | 0
10 | Company Management | 8 | 19 | 27
11 | Department Management | 0 | 0 | 0
12 | Manager Inventory | 0 | 0 | 0
13 | Settings | 0 | 0 | 0
Total |  | 108 | 117 | 225